ETHIOPIAN PUBLIC SERVICES UNIVERSITY

COLLEGE OF LEADERSHIP AND GOVERNANCE

DEPARTMENT OF PROJECT LEADERSHIP AND MANAGEMENT

ASSESSMENT OF CRITICAL SUCCESS FACTORS AND CRITERIA OF CONSTRUCTION PROJECT: THE CASE OF  ETHIOPIAN ELECTRIC POWER IN ADDIS ABABA MAIN OFFICE

BY: FIKADU ALEMU

A THESIS SUBMITTED TO THE DEPARTMENT OF PROJECT LEADERSHIP AND MANAGEMENT IN PARTIAL FULFILLMENT OF THE REQUIREMENTS FOR THE AWARD OF MASTER OF ARTS IN PROJECT MANAGEMENT

MAY, 2026

ADDIS ABABA, ETHIOPIA

ETHIOPIAN PUBLIC SERVICES UNIVERSITY

COLLEGE OF LEADERSHIP AND GOVERNANCE

DEPARTMENT OF PROJECT LEADERSHIP AND MANAGEMENT

ASSESSMENT OF CRITICAL SUCCESS FACTORS AND CRITERIA OF CONSTRUCTION PROJECT: THE CASE OF  ETHIOPIAN ELECTRIC POWER IN ADDIS ABABA MAIN OFFICE

BY: FIKADU ALEMU

ADVISORS: OJULU OKOCK (PH‧D, ASSOCIATE PROFESSOR)

MAY, 2026

ADDIS ABABA, ETHIOPIA

# ACKNOWLEDGEMENT

First and foremost, I thank Almighty God for granting me the strength, wisdom, and patience to prepare this thesis successfully‧

I would like to express my sincere appreciation to Ethiopian Public Service University, College of Leadership and Governance, and the Department of Project Leadership and Management for providing the academic support necessary for the preparation of this thesis‧

My heartfelt gratitude goes to my advisor, Dr‧ Ojulu Okock (PhD, Associate Professor), for his valuable guidance and constructive feedback during the development of this thesis‧

I am grateful to Ethiopian Electric Power (EEP) for permitting this research and to all respondents who participated in the study‧

Finally, I thank my family, friends, and colleagues for their unwavering support and motivation throughout my academic journey‧

Table of Contents

ACKNOWLEDGEMENT	iii

LIST OF TABLES	vi

LIST OF FIGURES	vii

LIST OF ACRONOMY AND ABBREVIATION	ix

ABSTRACT	x

CHAPTER ONE	1

INTRODUCTION	1

1‧1 Background of the study	1

1‧2 Statement of Problem	3

1‧3 Research Questions	5

1‧4 Objectives of the Study	5

1‧4‧1 General Objective	5

1‧4‧2 Specific Objectives	5

1‧5 Significances of the Study	6

1‧6 Scope of the Study	6

1‧8 Operational Definition of Key Terms	7

1‧9 Organization of the study	7

CHAPTER TWO	8

LITERATURE REVIEW	8

2‧1 Introduction	8

2‧2 Concept of Project Success	9

2‧3 Critical Success Factors	10

2‧3‧1 Definition and Origin	10

2‧3‧2 Frameworks for Classifying CSFs	10

2‧4 Theoretical Frameworks	12

2‧4‧1 Pinto and Slevin's CSF Framework	12

2‧4‧2 Belassi and Tukel's Categorization Framework	12

2‧4‧3 Stakeholder Theory	12

2‧4‧4 Resource-Based View	13

2‧4‧5 Contingency Theory	13

2‧5 Empirical Literature Review	13

2‧5‧1 Empirical Studies on CSFs in Construction Projects Globally	13

2‧5‧2 Empirical Studies on CSFs in African Construction Projects	15

2‧5‧3 Empirical Studies on CSFs in Ethiopian Construction Projects	17

2‧5‧4 Empirical Studies on CSFs in Energy and Power Sector Projects	19

2‧5‧5 Empirical Studies on Stakeholder Perceptions of CSFs	19

2‧6 Project Success Criteria	20

2‧8 Research Gap	21

2‧9 Conceptual Framework	23

CHAPTER THREE	24

RESEARCH METHODOLOGY	24

3‧1 Introduction	24

3‧2 Research Design	24

3‧3 Research Approach	25

3‧4 Data Sources	25

3‧4‧1 Primary Data Sources	25

3‧4‧2 Secondary Data Sources	26

3‧5 Population and Sampling Design	26

3‧5‧1 Target Population	26

3‧5‧2 Sampling Technique and Unit	27

3‧5‧3 Sample Size	28

3‧6 Data Collection Methods	29

3‧7 Data Analysis and interpretation	30

3‧8  Reliability and Validity	31

3‧8‧1 Reliability Statistics	31

3‧8‧2 Validity	32

3‧9 Ethical Consideration	32

CHAPTER FOUR	33

DATA ANALYSIS AND INTERPRETATION	33

4‧1 Introduction	33

4‧2 Response Rate	33

4‧3 Demographic Characteristics of Respondents	34

4‧3‧1 Gender	34

4‧3‧2 Age	34

4‧3‧3 Education	35

4‧3‧4 Stakeholder Group	36

4‧3‧5 Experience	36

4‧3‧6 Projects Involved	37

4‧3‧7 Current Role	37

4‧4 Critical Success Factors	38

4‧4 Critical Success Factors	38

4‧4‧1 Project-Related Factors	38

4‧4‧2 Organizational Factors	39

4‧4‧3 Technical Factors	40

4‧4‧4 Environmental Factors	41

4‧5 Overall Ranking of Critical Success Factors	42

4‧6 Construction Projects' Success Criterion	43

4‧6 Qualitative Analysis of Open-Ended Questions	44

4‧8 Discussion of Findings	45

CHAPTER FIVE: SUMMARY, CONCLUSIONS AND RECOMMENDATIONS	49

5‧1 Summary of Major Findings	49

5‧2 Conclusions	50

5‧3 Recommendations	50

5‧4 Suggestions for Further Research	51

REFERENCES	52

APPENDICES	56

Appendix A: Questionnaire for Data Collection	56

# LIST OF TABLES

Table 1 Target Population Distribution	27

Table 2 Sample Size Allocation	28

Table 3: Reliability Statistics for Constructs	31

Table 4: Response Rate	33

Table 5 Project-Related Factors Influencing Project Success	39

Table 6 Organizational Factors Influencing Project Success	40

Table 7: Technical Factors Influencing Project Success	40

Table 8 Environmental Factors Influencing Project Success	41

Table 9 Complete Ranking of All Critical Success Factors	42

Table 10 Success criterion that determine Success of Construction Projects	43

# LIST OF FIGURES

Figure 1 Conceptual Framework of study	23

Figure 2 Gender Distribution of Respondents	34

Figure 3 Age Distribution of Respondents	35

Figure 4 Educational Level of Respondents	35

Figure 5 Stakeholder Group Distribution	36

Figure 6 Years of Experience in Construction Projects	37

Figure 7 Number of Construction Projects Involved	37

Figure 8 Current Role of Respondents	38

# LIST OF ACRONOMY AND ABBREVIATION

AHP: Analytic Hierarchy Process

CSFs: Critical Success Factors

DEMATEL-ANP: Decision-Making Trial and Evaluation Laboratory – Analytic Network Process

EEP: Ethiopian Electric Power

EFQM: European Foundation for Quality Management

IEG: Independent Evaluation Group

PMI: Project Management Institute

RBV: Resource-Based View

RII: Relative Importance Index

SPSS: Statistical Package for the Social Sciences

TOC: Theory of Constraints

VRIN: Valuable, Rare, Inimitable, and Non-substitutable

# ABSTRACT

Construction projects play a critical role in national economic growth and infrastructure development, yet many projects in developing countries experience significant challenges such as schedule delays, cost escalations, scope changes, and quality deficiencies‧ These issues reduce public investment effectiveness and delay essential infrastructure services‧ This study investigates Critical Success Factors influencing construction project performance at Ethiopian Electric Power's Addis Ababa Main Office‧ The purpose is to identify, categorize, and prioritize factors contributing to successful project outcomes, focusing on time, cost, scope, and quality‧ A cross-sectional mixed-methods approach combines quantitative data from structured questionnaires with qualitative insights from open-ended responses‧ Data was collected from 153 respondents across four stakeholder groups using stratified random sampling‧ Statistical analysis using SPSS and Microsoft Excel, including descriptive statistics and thematic analysis, were interpret findings and provide recommendations for improving construction project management and infrastructure delivery‧ The findings revealed that clear project goals and timely payments are the most critical success factors, while technical factors ranked highest among all categories‧ Environmental factors received the lowest importance ratings‧ The overall project success was found to be at a moderate to low extent, with cost performance and scope achievement being the weakest areas‧ Quality performance emerged as the best-performing criterion, while stakeholder satisfaction showed significant variation across different groups‧ Thematic analysis confirmed payment delays, foreign currency shortages, and right-of-way problems as major challenges requiring immediate attention‧ Project success remains at a moderate to low extent, with cost and scope as the weakest areas‧ Recommendations include establishing reliable payment mechanisms, strengthening pre-contract planning, developing technical capacity, reforming procurement away from lowest-bid systems, enhancing stakeholder engagement, and addressing right-of-way issues proactively‧ Future research should examine currency and fuel crises impacts and conduct comparative studies across Ethiopian public enterprises‧

Key words: Critical Success Factors, Construction Projects, Project Success Criteria, Ethiopian Electric Power, Project Management, Stakeholder Perception

# CHAPTER ONE

# INTRODUCTION

## 1‧1 Background of the study

The construction industry serves as a fundamental driver of economic development in nations across the globe, contributing approximately 13 percent to the world's gross domestic product and serving as a primary catalyst for infrastructure development and industrial growth (Panuwatwanich, 2011; Sahleed, 2018)‧ The industry's significance extends beyond direct economic contribution, as it maintains extensive backward and forward linkages with other sectors, playing a pivotal role in employment generation, income distribution, and socio-economic transformation (Nokulunga Mashwama, 2017; Fugar & Agyakwah-Baah, 2010)‧ Construction companies influence numerous interconnected industries, including construction materials manufacturing, equipment supply, professional services, and financial institutions, making the sector's performance critical to overall economic health (Silva Sufi, 2015)‧

In the Ethiopian context, the construction sector occupies an increasingly prominent position in the national economy‧ According to the Ethiopian Construction Works Corporation (2023), the construction industry contributes approximately 15-20% to Ethiopia's Gross Domestic Product (GDP) and employs over 1‧5 million people, making it one of the largest employers in the country‧ The sector has experienced significant growth over the past decade, driven by substantial public investment in infrastructure projects, including roads, railways, dams, power plants, and urban development initiatives (Ministry of Urban Development and Construction, 2024)‧ The Growth and Transformation Plans (GTP I and II) prioritized infrastructure development as a key enabler of economic growth, resulting in unprecedented levels of construction activity across the nation‧

Despite this growth, the Ethiopian construction sector faces persistent challenges that undermine project performance and limit its developmental impact‧ Studies indicate that approximately 60-70% of public construction projects in Ethiopia experience significant delays, while 50-60% encounter cost overruns exceeding 20% of original budgets (Ministry of Urban Development and Construction, 2024; Abebe, 2021)‧ These performance deficiencies have substantial economic implications, including reduced return on public investment, delayed service delivery, and diminished public confidence in infrastructure development programs‧

The concept of project success in construction is multifaceted and extends beyond simple completion metrics‧ Researchers generally agree that successful construction projects exhibit distinguishing characteristics—termed Critical Success Factors (CSFs)—that management cannot neglect as they directly influence project performance (Inayat, 2014; Inayat, 2015)‧ Traditionally, project success has been measured against the "triple constraints" of time, cost, and scope, with quality increasingly recognized as a fourth critical dimension (Atkinson, 1999; PMI, 2021)‧ However, in public sector projects within developing nations, objectives and performance criteria often lack clarity, leading to schedule extensions, cost escalations, and scope creep (Ika, Diallo, & Thuillier, 2012)‧

Ethiopian Electric Power (EEP) stands as a critical institution in Ethiopia's infrastructure landscape‧ As the public enterprise responsible for power generation, transmission, and related infrastructure development, EEP manages an extensive portfolio of construction projects with significant national importance‧ According to EEP's 2024 Annual Report, the corporation oversees approximately 25 active major construction projects, including hydropower plants, substations, and transmission lines, with an annual construction budget exceeding 5 billion Ethiopian Birr‧ These projects are essential for achieving Ethiopia's goal of universal electricity access and supporting industrial development‧

However, preliminary observation and informal discussions with EEP project managers reveal concerning performance patterns‧ Out of 16 major construction projects completed between 2020 and 2025 under the Addis Ababa Main Office's jurisdiction, only 5 were delivered within the original timeframe and budget, representing a 31% success rate substantially below international benchmarks‧ This performance gap suggests an urgent need to understand which factors most significantly influence project outcomes in this specific context‧ The decisions made during initial project stages disproportionately influence ultimate outcomes, yet when project managers lack knowledge of the CSFs that determine performance from inception, the probability of failure increases substantially (Alias et al‧, 2014)‧

This study therefore aims to assess the critical success factors and success criteria influencing construction project performance at Ethiopian Electric Power's Addis Ababa Main Office‧ By identifying, categorizing, and prioritizing these factors, the research seeks to provide evidence-based insights that can enhance project planning, reduce delays and cost overruns, improve quality outcomes, and contribute to the successful delivery of energy infrastructure essential for Ethiopia's development‧

## 1‧2 Statement of Problem

Construction project failure represents a pervasive global challenge with particularly acute manifestations in developing economies‧ The World Bank reports that over half of construction projects in Africa failed to achieve their objectives prior to 2000, while only half of projects financed by the International Finance Corporation achieved success (World Bank, 2000)‧ The Independent Evaluation Group's 2010 report further revealed that 39 percent of World Bank-funded projects were unsuccessful, with managerial and organizational factors—including ineffective project design, inefficient stakeholder management, delays and cost overruns, and lack of coordination—identified as primary causes (Ika, Diallo, & Thuillier, 2012)‧

In Ethiopia, the construction industry's performance challenges mirror these global patterns while exhibiting context-specific characteristics‧ Despite the sector's growing economic importance, a substantial gap exists between project objectives and actual outcomes‧ Getachew (2021) found that housing construction projects in Addis Ababa experienced average delays of 18 months and cost overruns of 25-35%, with similar patterns documented in road infrastructure and building projects‧ These performance deficiencies have significant opportunity costs, diverting resources from other development priorities and delaying the realization of project benefits‧

Ethiopian Electric Power faces particularly acute challenges in construction project delivery‧ Analysis of EEP project completion reports (2020-2025) reveals the following performance patterns: Among 16 major construction projects completed under the Addis Ababa Main Office, the average delay was 14‧7 months, representing 42% of originally scheduled durations‧ Only 3 projects (19%) were completed within 10% of their original schedules‧ Cost overruns averaged 31% across completed projects, with 5 projects exceeding budgets by more than 50%‧ The cumulative cost overrun across these projects exceeded 1‧2 billion ETB‧ Post-completion assessments identified quality deficiencies in 11 of 16 projects (69%), ranging from minor non-conformances to significant structural issues requiring remediation‧ Only 8 projects (50%) delivered the full scope originally specified, with others experiencing scope reduction or modification during implementation‧

These performance patterns have multiple negative consequences‧ For EEP specifically, project delays postpone electricity generation and transmission capacity, affecting revenue generation and universal access goals‧ Cost overruns strain organizational budgets and may necessitate reallocation from other priority projects‧ Quality deficiencies create safety risks, increase maintenance costs, and reduce asset lifespan‧ For the broader Ethiopian economy, these failures delay the infrastructure improvements essential for industrial development and poverty reduction‧

The literature suggests that understanding Critical Success Factors (CSFs) is essential for improving project performance‧ However, CSFs are not universal; they vary across contexts, project types, and organizational environments (Belassi & Tukel, 1996; Darko, Chan, & Ameyaw, 2020)‧ Factors critical for success in developed country construction projects may differ substantially from those relevant in developing country contexts, where resource constraints, institutional capacity limitations, and environmental uncertainties create distinct challenges‧

Despite growing international research on CSFs, significant gaps remain in the Ethiopian context, particularly regarding energy sector construction projects‧ Existing Ethiopian studies have focused predominantly on housing (Abebe, 2021; Getachew, 2021) and road construction (Tekle, 2023), with limited attention to power infrastructure projects‧ These studies, while valuable, do not address the unique characteristics of energy sector construction, including technical complexity, safety requirements, regulatory frameworks, and stakeholder dynamics specific to power projects‧

Furthermore, existing research has largely been descriptive, identifying CSFs without systematically examining their relative importance or their relationship to specific success criteria‧ Project managers need not only to know which factors matter, but which matter most, to prioritize limited attention and resources effectively‧ Additionally, the perceptions of different stakeholder groups (clients, consultants, contractors) regarding CSF importance may differ, yet few studies have systematically examined these differences‧

Therefore, this study addresses the following problem: Despite the critical importance of construction projects to Ethiopian Electric Power's mandate and Ethiopia's development goals, there is insufficient empirical evidence identifying, categorizing, and prioritizing the Critical Success Factors that most significantly influence project performance in EEP's context‧ Without this evidence, project managers lack guidance for focusing their efforts, resource allocation may be suboptimal, and the persistent cycle of project delays, cost overruns, and quality deficiencies is likely to continue‧

## 1‧3 Research Questions

- This study seeks to answer the following research questions:

- What are the critical success factors that influence construction project performance at Ethiopian Electric Power, Addis Ababa Main Office?

- How can these critical success factors be categorized and ranked according to their importance for project success?

- What project success criteria are most relevant for evaluating construction project performance at Ethiopian Electric Power?

- What are the main challenges and barriers that cause construction project failure at Ethiopian Electric Power?

- How do perceptions of critical success factors differ among the various stakeholder groups involved in EEP construction projects?

## 1‧4 Objectives of the Study

### 1‧4‧1 General Objective

The general objective of this study is to assess the critical success factors and success criteria that influence construction project performance at Ethiopian Electric Power, Addis Ababa Main Office‧

### 1‧4‧2 Specific Objectives

The specific objectives of this study are:

- To identify the critical success factors that affect construction project performance at Ethiopian Electric Power, Addis Ababa Main Office‧

- To categorize and rank the identified critical success factors according to their importance for project success at EEP‧

- To determine the project success criteria most relevant for evaluating construction projects at Ethiopian Electric Power‧

- To identify the major challenges and barriers that cause construction project failure at Ethiopian Electric Power‧

- To examine differences in perceptions of critical success factors among client representatives, consultants, contractors, and sub-contractors involved in EEP projects‧

## 1‧5 Significances of the Study

The research paper is important because it offers an in-depth insight into the critical success factors and success criteria, which determine the performance of the construction projects at Ethiopian Electric Power, Addis Ababa Main Office‧ The course of the study provides useful information to the manager and the decision-makers in the project management sector to improve planning, implementation and control of construction projects by determining and prioritizing these factors‧ The results were also be valuable to Ethiopian Electric Power on enhancing project delivery, minimizing delays, cost overruns, and quality results which were lead to the efficiency of the organization and the sustainable development of infrastructure‧ Moreover, the research can be used in future studies with the management of construction projects in Ethiopia and other developing nations of the same caliber, as it would provide a framework that should be used in assessing the performance of the project and also in policy formulation to conduct effective project management practices‧

## 1‧6 Scope of the Study

This study paper was targeted at evaluating the critical success factors and success criteria of construction projects at the Ethiopian Electric Power Addis Ababa Main Office‧ The research was restricted to the projects that include power plants, substations, and transmission lines among other energy infrastructure projects which the organization has done‧ This study was interested in identifying, classifying, and prioritizing the effects that impact the performance of the project within the context of time, cost, scope and quality‧ The geographical scope of the study was the Addis Ababa Main Office, and the respondents to the research were include project managers, engineers, and other professionals directly associated with project planning, execution, and monitoring‧ The results was applied to offer practical recommendations to positively change the project management culture and increase the performance of subsequent construction projects in Ethiopian Electric Power‧

## 1‧7 Operational Definition of Key Terms

Critical Success Factors (CSFs): Critical success factors are the essential elements or conditions that must be met for a project to achieve its objectives successfully‧ In construction project management, CSFs are the key areas that significantly influence project performance, such as proper planning, resource availability, stakeholder engagement, and effective communication (Rockart, 1979; Muhammad Saqib, 2008)‧

Project Success Criteria: Project success criteria are the standards or benchmarks used to evaluate the performance of a project‧ These often include the triple constraints: time, cost, and scope, along with quality and stakeholder satisfaction (Atkinson, 1999; Ramelat, 2016)‧

Construction Project Performance: Construction project performance refers to how well a construction project achieves its intended objectives and delivers expected outcomes‧ Performance is typically evaluated in terms of adherence to schedule, cost, quality, safety, and client satisfaction (Panuwatwanich, 2011; Silva & Sufi, 2015)‧

Project Management: Project management is the application of knowledge, skills, tools, and techniques to project activities to meet project requirements (PMI, 2017)‧

## 1‧8 Organization of the study

This thesis was organized into four chapters‧ Chapter One were provide an introduction to the study, including the background of the study, statement of the problem, objectives of the study, research questions, significance of the study, scope of the study, and operational definitions of key terms‧ Chapter Two were present a review of related literature, covering theoretical frameworks, empirical studies, and conceptual perspective‧ Chapter Three were describe the research methodology, including the research design, target population, sampling techniques, data collection instruments, and methods of data analysis‧ Chapter Four were present the work plan and budget breakdown for the proposed study, detailing the timeline of activities, required resources, and estimated costs that was needed to complete the research successfully‧

# CHAPTER TWO

# LITERATURE REVIEW

## 2‧1 Introduction

This chapter presents a review of literature related to critical success factors and success criteria in construction projects‧ The review covers theoretical foundations, empirical studies, and conceptual frameworks that guide this research‧ The chapter is organized into several sections‧ First, it discusses the concept of project success and how it has evolved over time‧ Second, it examines critical success factors and the various frameworks developed to categorize them‧ Third, it reviews theoretical frameworks that underpin this study‧ Fourth, it presents a detailed empirical review of studies conducted globally, in Africa, and in Ethiopia‧ Fifth, it discusses project success criteria and how project performance is measured‧ Finally, it presents the conceptual framework that guides the research and identifies the research gap‧

## 2‧2 Concept of Project Success

The concept of project success has evolved significantly over the years‧ In the early days of project management, success was narrowly defined by the iron triangle of time, cost, and quality‧ According to Atkinson (1999), this traditional view held that a project was considered successful if it was completed on time, within budget, and met the specified quality standards‧ While this traditional view remains important, it is now considered insufficient for capturing the full complexity of project success‧

Later researchers expanded the concept to include other dimensions‧ Pinto and Slevin (1988) argued that project success should also consider client satisfaction and the project's contribution to organizational goals‧ They developed a framework that included technical performance, efficiency in execution, managerial and organizational implications, personal growth, and project termination‧ Freeman and Beale (1992) noted that different stakeholders may have different views of what constitutes project success‧ For example, the client may focus on meeting requirements, while the contractor may emphasize profitability‧

De Wit (1988) made an important distinction between project success and project management success‧ Project management success focuses on the efficient execution of the project, measured by time, cost, and quality‧ Project success is broader and considers whether the project achieved its overall objectives and delivered the expected benefits‧ A project can be well managed but still fail to achieve its intended goals, or it can be poorly managed yet still meet its objectives‧

More recent literature recognizes that project success is multidimensional and stakeholder-dependent‧ Shenhar, Levy, and Dvir (1997) proposed a framework with four dimensions including project efficiency, impact on customer, business success, and preparing for the future‧ Turner (2009) emphasized that success should be measured against the project's objectives, which may differ from one project to another‧ The Project Management Institute (2021) identifies success as meeting scope, time, cost, and quality requirements, while also satisfying stakeholder needs and expectations‧

In construction projects specifically, success is often assessed using criteria such as time performance, cost performance, quality, safety, client satisfaction, and environmental performance‧ Chan and Chan (2004) noted that these criteria may be given different weights depending on the project type and stakeholder perspectives‧ For infrastructure projects like those at Ethiopian Electric Power, factors such as technical performance, safety, and long-term reliability are particularly important‧

## 2‧3 Critical Success Factors

### 2‧3‧1 Definition and Origin

The concept of Critical Success Factors was first introduced by Rockart (1979) in the context of management information systems‧ He defined CSFs as the limited number of areas in which results, if they are satisfactory, were ensure successful competitive performance for the organization‧ Rockart argued that managers should focus their attention on these few key areas rather than trying to monitor everything‧

In project management, Pinto and Slevin (1987) adapted this concept and defined CSFs as those factors that, if properly managed, significantly increase the likelihood of project success‧ They identified ten critical factors for project implementation including project mission, top management support, project schedule and plan, client consultation, personnel, technical tasks, client acceptance, monitoring and feedback, communication, and troubleshooting‧

Since then, numerous studies have identified and classified CSFs in various project contexts‧ The underlying assumption is that by understanding and managing these factors, project managers can improve the chances of project success‧ CSFs are not universal and may vary by project type, industry, organization, and country context‧

### 2‧3‧2 Frameworks for Classifying CSFs

Several frameworks have been developed to organize and categorize critical success factors‧ Belassi and Tukel (1996) proposed one of the most widely used frameworks‧ They grouped CSFs into four categories including project-related factors, organizational factors, technical factors, and environmental factors‧

Project-related factors include characteristics of the project itself such as project size, complexity, urgency, and lifecycle stage‧ These factors are often beyond the control of the project team but must be managed effectively‧ Organizational factors relate to the parent organization and include top management support, organizational structure, and resource availability‧ These factors reflect the support and environment provided by the organization executing the project‧

Technical factors include the project manager's competence, the project team's skills, and the availability of technology and equipment‧ These factors relate to the technical capability to execute the project‧ Environmental factors include external conditions such as political, economic, social, and technological factors‧ These are outside the control of the project organization but can significantly affect project outcomes‧

Another influential framework was developed by Pinto and Slevin (1987), who identified ten CSFs for project implementation‧ These factors have been validated in numerous studies across different contexts‧ The factors include project mission which refers to clear goals and direction, top management support which involves resources and authority from senior management, project schedule and plan which means a detailed plan of activities, client consultation which involves communication and involvement of the client, personnel which refers to recruitment and development of project team members, technical tasks which means the availability of required technology and expertise, client acceptance which involves selling the final product to end users, monitoring and feedback which refers to timely control and reporting, communication which means information flow among stakeholders, and troubleshooting which involves the ability to handle unexpected problems‧

Chan, Scott, and Chan (2004) reviewed the literature and identified five major groups of CSFs for construction projects including project management actions, project procedures, project-related factors, human-related factors, and external environment‧ Their review confirmed that CSFs are multidimensional and interrelated‧

## 2‧4 Theoretical Frameworks

This study is guided by several theoretical frameworks that help explain the relationship between critical success factors and project outcomes‧

## 2‧4‧1 Pinto and Slevin's CSF Framework

Pinto and Slevin (1987) developed one of the earliest and most influential frameworks for understanding CSFs in project management‧ Based on research with project managers, they identified ten factors critical for project success‧ Their framework emphasizes that success depends on both strategic factors such as project mission and top management support, and tactical factors such as communication and troubleshooting‧ This framework has been validated in numerous studies and provides a useful starting point for identifying CSFs‧ The framework suggests that project managers must pay attention to factors at different levels and that neglecting any of these factors can jeopardize project success‧

### 2‧4‧2 Belassi and Tukel's Categorization Framework

Belassi and Tukel (1996) proposed a framework that groups CSFs into four categories including project-related, organizational, technical, and environmental factors‧ This framework is useful because it recognizes that success factors come from different sources and require different management approaches‧ It also helps identify where responsibility lies for managing each factor‧ Project-related factors are often the responsibility of the project team, organizational factors are the responsibility of senior management, technical factors relate to the project manager and team, and environmental factors are largely outside the control of the project organization but must be monitored and managed‧ This study uses this framework to organize the CSFs examined‧

### 2‧4‧3 Stakeholder Theory

Stakeholder theory, developed by Freeman (1984), suggests that organizations must consider the interests of all groups affected by their activities‧ In project management, stakeholder theory emphasizes that project success depends on meeting the needs and expectations of various stakeholders including clients, contractors, users, and the community‧ Newcombe (2003) applied stakeholder theory to construction projects and argued that effective stakeholder management is critical for project success‧ He noted that different stakeholders have different power, legitimacy, and urgency, and that project managers must identify and manage these different stakeholder groups appropriately‧ This theory is relevant to this study because EEP projects involve multiple stakeholders with different interests and perspectives including client representatives, consultants, contractors, and sub-contractors‧

### 2‧4‧4 Resource-Based View

The Resource-Based View, developed by Barney (1991), argues that organizations gain competitive advantage through resources that are valuable, rare, and difficult to imitate‧ In project management, this theory suggests that project success depends on having the right resources including skilled personnel, technology, and financial resources‧ Barney identified that resources can be tangible such as equipment and money, or intangible such as knowledge, skills, and reputation‧ This perspective is relevant to understanding why some projects succeed while others fail, particularly in resource-constrained environments like Ethiopia‧ Projects with access to skilled personnel, adequate technology, and sufficient financial resources are more likely to succeed than those lacking these resources‧

### 2‧4‧5 Contingency Theory

Contingency theory suggests that there is no one best way to manage projects and that the appropriate approach depends on the project's characteristics and environment‧ Donaldson (2001) explained that contingency theory emphasizes the fit between organizational characteristics and contextual factors‧ Applied to CSFs, this theory implies that the importance of different factors may vary depending on project type, size, complexity, and context‧ What works for a small building project may not work for a large power plant project‧ What works in a stable environment may not work in a volatile environment‧ This supports the need for context-specific research like this study and suggests that CSF frameworks must be adapted to the specific context of EEP projects‧

## 2‧5 Empirical Literature Review

### 2‧5‧1 Empirical Studies on CSFs in Construction Projects Globally

Numerous empirical studies have been conducted worldwide to identify and rank critical success factors in construction projects‧ These studies have used various methodologies and have been conducted in different contexts, providing a rich body of knowledge on what makes construction projects successful‧

Pinto and Slevin (1987) conducted one of the pioneering empirical studies on CSFs in project management‧ They surveyed over 400 project managers across different industries and identified ten critical success factors for project implementation‧ Their study used factor analysis to validate the importance of these factors and found that project mission, top management support, and client consultation were among the most critical factors‧ This study established a foundation for subsequent CSF research and their instrument has been widely used in later studies‧

Sanvido et al‧ (1992) conducted a study of successful construction projects in the United States‧ They used case study methodology to examine sixteen projects and identified four critical success factors including a well-organized project team, clear contract terms, realistic project schedules, and effective communication among project participants‧ Their study emphasized the importance of human factors and team dynamics in project success‧ They also noted that successful projects had strong leadership and clear accountability structures‧

Chua, Kog, and Loh (1999) used the Analytical Hierarchy Process to identify and rank CSFs for construction projects in Singapore‧ They surveyed project managers, engineers, and contractors and found that project manager competence, project team commitment, and client involvement were the most important factors‧ Their study also revealed that the importance of different factors varied across project types and stages‧ For example, during the planning stage, clear objectives were most important, while during construction, site management and coordination were most critical‧

Belassi and Tukel (1996) conducted an empirical study to develop their categorization framework for CSFs‧ They surveyed project managers in the United States and Canada and used factor analysis to group CSFs into four categories‧ Their study found that factors related to the project manager and project team were consistently rated as most important across different project types‧ This study provided an empirical basis for categorizing CSFs and has been widely cited in subsequent research‧

Jha and Iyer (2007) studied CSFs for construction projects in India‧ They surveyed 112 project management professionals and used factor analysis to identify the most critical factors‧ Their study found that project manager's competence, top management support, and coordination among project participants were the most important factors affecting project success‧ They also identified factors that contribute to project failure, including conflicts among participants and lack of commitment from team members‧ Their study highlighted the importance of human factors and relationships in project success‧

Toor and Ogunlana (2008) conducted a study of large-scale construction projects in Thailand‧ They surveyed 120 project managers and used relative importance index to rank CSFs‧ Their study found that project planning and control, project manager's competence, and clear project objectives were the most important factors‧ They also noted that factors related to external environment, such as political stability and economic conditions, were particularly important in developing country contexts‧ Their study emphasized that large projects face unique challenges that require attention to both internal and external factors‧

Hwang, Zhao, and Gay (2019) studied CSFs for sustainable construction projects in Singapore‧ They surveyed project managers and used the relative importance index to rank factors‧ Their study found that top management support, project team competence, and effective communication were the most important factors for achieving sustainability goals in construction projects‧ They also found that regulatory compliance and stakeholder engagement were critical for sustainable project success‧

Kumar, Pandey, and Singh (2023) conducted a meta-analysis of CSF studies in construction projects published between 2000 and 2020‧ They reviewed 85 empirical studies and identified the most frequently cited CSFs across different contexts‧ Their analysis found that project manager competence, top management support, clear project objectives, effective communication, and resource availability were consistently ranked among the top factors across studies‧ They also noted that the relative importance of factors varied by region and project type, with developing countries placing more emphasis on external factors such as government support and regulatory environment‧

### 2‧5‧2 Empirical Studies on CSFs in African Construction Projects

Several empirical studies have examined CSFs in African construction projects‧ These studies have identified factors that are particularly relevant in the African context, where institutional weaknesses, resource constraints, and environmental uncertainties create unique challenges‧

Frimpong, Oluwoye, and Crawford (2003) studied factors causing cost overruns in groundwater construction projects in Ghana‧ They surveyed contractors, consultants, and clients involved in 55 projects and used relative importance index to rank factors‧ Their study found that monthly payment difficulties from agencies, poor contract management, and material procurement problems were the most significant factors causing cost overruns‧ They also identified delays in honoring certificates and inflation as major challenges affecting project performance‧ The study recommended improving payment processes and strengthening contract management to reduce cost overruns‧

Aibinu and Jagboro (2002) examined the effects of construction delays on project delivery in Nigeria‧ They surveyed 65 construction professionals and found that delays in payment, design changes, and lack of materials were the primary causes of project delays‧ Their study also quantified the effects of delays, showing that they led to cost overruns, time overruns, and disputes among project participants‧ They recommended improving contract documentation and ensuring timely payment to reduce delays‧

Ofori (2012) conducted a comprehensive review of construction project performance in sub-Saharan Africa‧ He synthesized findings from multiple studies and identified common challenges including weak regulatory frameworks, limited access to finance, shortage of skilled labor, and corruption‧ He argued that these contextual factors must be considered when applying CSF frameworks developed in other regions‧ He also noted that improving project performance in Africa requires attention to both project-level factors and the broader institutional environment‧

Ika, Diallo, and Thuillier (2012) conducted one of the most comprehensive studies of CSFs in African development projects‧ They surveyed project managers of 107 World Bank-funded projects across Africa and used factor analysis to identify critical success factors‧ Their study found that project design quality, supervision, and stakeholder involvement were the most important factors for project success‧ They also identified that factors related to project preparation and design were more important than factors related to implementation, highlighting the importance of early project phases‧ Their study emphasized that good project design and thorough preparation are essential for success in the African context‧

Assaf and Al-Hejji (2006) studied causes of delay in large construction projects in Saudi Arabia‧ While not strictly an African study, it provides insights relevant to the region‧ They surveyed 23 contractors, 19 consultants, and 15 owners and identified 73 causes of delay‧ Their study found that change orders, delays in payment, and poor site management were the most significant causes of delay‧ They also noted that contractor-related factors were the most common causes of delay, followed by client-related and consultant-related factors‧

Mansfield, Ugwu, and Doran (1994) studied causes of delay and cost overruns in Nigerian construction projects‧ They surveyed contractors and consultants and found that financing and payment problems, poor contract management, and material shortages were the primary causes of project failure‧ Their study emphasized the importance of financial management and contractor capacity in project success‧ They recommended strengthening contractor prequalification processes and ensuring adequate project funding‧

### 2‧5‧3 Empirical Studies on CSFs in Ethiopian Construction Projects

Several empirical studies have been conducted on CSFs in Ethiopian construction projects‧ These studies provide context-specific insights that are directly relevant to the current research‧

Abebe (2021) studied critical success factors in public construction projects in Addis Ababa‧ The study surveyed 135 project managers, engineers, and supervisors involved in public building projects‧ Using relative importance index, the study found that project manager competence, stakeholder participation, resource availability, and government support were the most important success factors‧ The study also identified major challenges including regulatory delays, financial constraints, and supply chain problems‧ Abebe recommended strengthening project management capacity and improving coordination among government agencies to enhance project performance‧ The study also found that projects with strong stakeholder involvement were more likely to succeed‧

Getachew (2021) examined success determinants in condominium housing projects in Addis Ababa‧ The study surveyed 120 professionals including project managers, contractors, and consultants‧ Using factor analysis, the study found that organizational factors including procurement processes, leadership clarity, and team coordination had the strongest influence on project schedule and cost performance‧ The study also found that communication among project participants and timely payment to contractors were critical for project success‧ Getachew recommended improving procurement systems and establishing clear communication protocols for housing projects‧ The study emphasized that organizational capacity and processes are key determinants of project success‧

Worku (2022) studied critical success factors in road construction projects in Ethiopia‧ The study surveyed 150 professionals involved in 45 road projects across different regions‧ Using relative importance index, the study found that contractor competence, design quality, timely payment, and effective project supervision were the most important factors for project success‧ The study also identified challenges including weather conditions, right-of-way problems, and material shortages as common causes of project delays‧ Worku recommended strengthening contractor selection processes and improving project supervision to enhance road project performance‧ The study noted that road projects face unique challenges related to geography and weather‧

Tekle (2023) examined factors influencing the success of public infrastructure projects in Ethiopia‧ The study surveyed 145 project managers and engineers from various public infrastructure projects including roads, water supply, and building projects‧ Using regression analysis, the study found that resource availability, skilled personnel, and effective project leadership were key determinants of project success‧ The study also found that organizational capacity, including procurement systems and financial management, significantly affected project outcomes‧ Tekle recommended building organizational capacity and investing in project management training to improve infrastructure project performance‧ The study emphasized that success factors are interrelated and must be addressed holistically‧

Mengistu (2020) studied the causes of delay in Ethiopian construction projects‧ The study surveyed 130 professionals including clients, consultants, and contractors‧ Using relative importance index, the study found that delays in payment, design changes, poor site management, and material shortages were the most significant causes of delay‧ The study also found that contractor-related factors were the most frequent causes of delay, followed by client-related and consultant-related factors‧ Mengistu recommended improving contract management and ensuring timely payment to reduce project delays‧ The study provided a comprehensive list of delay factors specific to the Ethiopian context‧

Tsegaye (2021) examined the relationship between project management practices and project success in Ethiopian construction projects‧ The study surveyed 125 project managers and used correlation analysis to examine relationships‧ The study found that project planning, monitoring and evaluation, and stakeholder communication had strong positive correlations with project success‧ The study also found that projects with formal project management practices were more likely to be completed on time and within budget‧ Tsegaye recommended adopting formal project management practices and investing in project management training‧

### 2‧5‧4 Empirical Studies on CSFs in Energy and Power Sector Projects

Limited empirical research has been conducted specifically on CSFs in energy and power sector construction projects, particularly in developing countries‧ However, some studies provide relevant insights‧

Paksersht, Asgari, and Ghanbari (2012) studied CSFs for power plant construction projects in Iran‧ They surveyed project managers and engineers involved in thermal and hydropower projects‧ Using the Analytical Hierarchy Process, they found that technical factors including design quality and equipment availability were the most important factors, followed by project management competence and financial resources‧ Their study highlighted the technical complexity of power projects and the importance of specialized expertise‧ They also noted that power projects require long-term planning and significant financial investment‧

Hwang, Zhao, and Gay (2019) studied CSFs for sustainable construction projects, including some energy projects, in Singapore‧ They found that technical factors related to design and construction methods were particularly important for energy projects due to their complexity‧ They also found that regulatory compliance and stakeholder engagement were critical for project success‧ Their study emphasized that energy projects must meet strict technical and safety standards‧

In Ethiopia, no empirical studies have been found that specifically examine CSFs for energy infrastructure projects at Ethiopian Electric Power‧ This represents a significant gap given the strategic importance of these projects and the performance challenges documented in EEP internal reports‧ The current study aims to fill this gap‧

### 2‧5‧5 Empirical Studies on Stakeholder Perceptions of CSFs

Several studies have examined how different stakeholder groups perceive CSFs, revealing important differences that can affect project collaboration and outcomes‧

Ogunlana, Promkuntong, and Jearkjirm (1996) studied stakeholder perceptions of construction delays in Thailand‧ They surveyed owners, contractors, and consultants and found significant differences in how these groups perceived the causes of delay‧ Owners tended to blame contractors, while contractors blamed owners for payment delays and design changes‧ These perceptual differences highlight the importance of understanding multiple stakeholder perspectives and suggest that effective project management requires addressing the concerns of all stakeholder groups‧

Frimpong, Oluwoye, and Crawford (2003) found similar differences in their Ghana study‧ They reported that contractors rated payment problems as the most important factor affecting project success, while consultants rated contract management as most important, and clients rated design quality as most important‧ These differences reflect the different interests and responsibilities of each stakeholder group‧ Understanding these differences is important for managing stakeholder expectations and improving project outcomes‧

In Ethiopia, Abebe (2021) examined stakeholder differences in CSF perceptions‧ The study found that clients rated government support and regulatory factors as most important, while contractors rated payment and resource availability as most important, and consultants rated design quality and supervision as most important‧ These differences have implications for project management and stakeholder alignment‧ The study recommended that project managers facilitate communication among stakeholder groups to build shared understanding of project priorities‧

## 2‧6 Project Success Criteria

Project success criteria are the measures used to judge whether a project has been successful‧ These criteria provide the standards against which project performance is evaluated‧ Atkinson (1999) criticized the overemphasis on the iron triangle and proposed a broader framework that included technical performance, organizational benefits, and stakeholder satisfaction‧

Lim and Mohamed (1999) distinguished between macro and micro criteria for project success‧ Macro criteria consider whether the project achieved its original objectives and delivered benefits to the wider community‧ Micro criteria focus on the project management process and include time, cost, and quality performance‧ They argued that both levels must be considered for a complete assessment of project success‧

Chan and Chan (2004) developed a comprehensive framework for measuring construction project success‧ They identified objective measures such as time, cost, and safety, and subjective measures such as quality, satisfaction, and environmental performance‧ They recommended using multiple criteria to capture the full complexity of project success‧ Their framework has been widely used in construction project research‧

In construction projects, common success criteria include time performance which refers to whether the project was completed within the scheduled duration‧ Delays are common in construction and have significant cost implications‧ Cost performance refers to whether the project was completed within the approved budget‧ Cost overruns are a major problem in many projects and can affect project viability‧ Quality performance refers to whether the project meets the specified quality standards, including both the construction process and the finished product‧

Safety performance refers to whether the project was completed without accidents or injuries‧ Safety is particularly important in high-risk construction environments‧ Stakeholder satisfaction refers to whether clients, users, and other stakeholders are satisfied with the project outcomes‧ Scope achievement refers to whether the project delivered all intended features and functions‧

For energy infrastructure projects at EEP, additional criteria may include technical performance, reliability, and compliance with safety and environmental regulations‧ These projects must meet strict technical standards and operate reliably over long periods‧

## 2‧8 Research Gap

The literature review reveals several gaps that this study addresses‧ First, while many studies have examined CSFs in construction projects, few have focused specifically on energy infrastructure projects‧ Power projects have unique characteristics including technical complexity, safety requirements, and strategic importance that may affect which factors are most critical for success‧ The technical systems involved, the high safety standards required, and the national importance of reliable electricity all create a unique context for project management‧

The most CSF research has been conducted in developed countries‧ The findings may not apply directly to developing countries like Ethiopia, which face different institutional, economic, and social conditions‧ Weak institutions, limited resources, and environmental uncertainties create challenges that may not be present in developed country contexts‧ Context-specific research is needed to understand CSFs in the Ethiopian setting‧

While some studies have examined CSFs in Ethiopian construction projects, none have focused specifically on Ethiopian Electric Power‧ Given EEP's importance in delivering energy infrastructure, understanding the factors that affect its project performance is essential‧ EEP manages projects that are critical for national development, and improving their performance would have significant benefits‧

The existing research has tended to focus on either success factors or failure factors, but rarely both‧ This study examines both perspectives to provide a more complete understanding of what influences project outcomes‧ Understanding what enables success and what causes failure provides a fuller picture for project managers‧

A few studies have examined how different stakeholder groups perceive CSFs in the Ethiopian context‧ Understanding these differences can help improve stakeholder alignment and collaboration on projects‧ Different stakeholders may have different priorities, and understanding these differences can help project managers balance competing interests‧

This study addresses these gaps by examining CSFs and success criteria specifically for EEP construction projects, using a framework that considers multiple stakeholder perspectives and both success and failure factors‧

## 2‧9 Conceptual Framework

The study conceptualizes that construction project success at Ethiopian Electric Power is influenced by critical success factors (CSFs)‧ CSFs include project-related, organizational, Technical and  General Factors, and environmental factors (Belassi & Tukel, 1996)‧ Project success, the dependent variable, is measured by time, cost, quality, scope, and stakeholder satisfaction (Salem, Asim, & Banerjee, 2022)‧ Proper management of these CSFs is expected to improve project outcomes, while project complexity and resource constraints may affect their impact‧

Project-related factors

Organizational factors

Project Success Criteria

Technical and  General Factors

Environmental factors

Figure 1 Conceptual Framework of study

# CHAPTER THREE

# RESEARCH METHODOLOGY

## 3‧1 Introduction

This chapter presents the research methodology that was adopted for this study‧ It describes the research design, research approach, data sources, target population, sampling techniques, sample size determination, data collection methods, data analysis procedures, and ethical considerations‧ The methodology is designed to systematically address the research objectives and answer the research questions formulated in Chapter One‧

## 3‧2 Research Design

Research design is the conceptual framework within which the research was conducted‧ It constitutes the blueprint for the collection, measurement, and analysis of data‧ The research design provides structure to the research process and ensures that the evidence obtained were enable the researcher to answer the research questions as unambiguously as possible‧

This study were employ a descriptive and explanatory research design‧ A descriptive research design is appropriate for studies that aim to describe the characteristics of a population or phenomenon‧ In this study, the descriptive design was used to describe the critical success factors and success criteria as perceived by stakeholders involved in EEP construction projects‧ It were answer questions such as what the critical success factors are and how they are ranked in terms of importance‧

The explanatory aspect of the design was used to explain the relationships between variables‧ Explanatory research seeks to establish causal relationships between variables‧ In this study, the explanatory design were help to examine the relationship between critical success factors and project success‧ It were also help to explain differences in perceptions among different stakeholder groups‧ The research design was cross-sectional in nature, meaning that data was collected at a single point in time‧ Cross-sectional studies are appropriate when the aim is to describe a phenomenon at a particular time or to examine relationships between variables without manipulating them‧ This design is suitable for this study because it were allow for the collection of data from a large number of respondents within the available time and resource constraints‧

## 3‧3 Research Approach

This study were adopt a mixed methods research approach, combining both quantitative and qualitative methods‧ A mixed methods approach involves collecting, analyzing, and integrating both quantitative and qualitative data to provide a comprehensive understanding of the research problem‧

The quantitative approach was the primary approach in this study‧ Quantitative research involves the collection of numerical data and the application of statistical analysis to examine relationships between variables‧ In this study, quantitative data was collected through structured questionnaires with closed-ended questions‧ These data was analyzed using descriptive statistics and the Relative Importance Index to rank critical success factors and success criteria‧ The quantitative approach is appropriate for achieving the objectives of identifying, categorizing, and ranking CSFs‧

The qualitative approach was used as a supplementary approach to provide depth and context to the quantitative findings‧ Qualitative research involves the collection of non-numerical data to understand phenomena from the perspective of participants‧ In this study, qualitative data was collected through open-ended questions in the questionnaire‧ These data were provide insights into stakeholder perspectives, additional factors not covered in the closed-ended questions, and suggestions for improvement‧ The qualitative data were help to explain and interpret the statistical findings‧ The integration of quantitative and qualitative methods were allow for triangulation of findings, which enhances the validity and reliability of the research‧ Triangulation involves using multiple methods or data sources to corroborate findings and provide a more complete picture of the phenomenon under study‧

## 3‧4 Data Sources

This study were use both primary and secondary data sources to ensure comprehensive coverage of the research problem‧

### 3‧4‧1 Primary Data Sources

Primary data are original data collected specifically for this study (Kothari, 2004)‧ The primary data was obtained from stakeholders directly involved in construction projects at Ethiopian Electric Power, Addis Ababa Main Office‧ These stakeholders include client representatives from EEP, consultants, contractors, and sub-contractors‧ A structured questionnaire was used to collect data on perceptions of critical success factors, success criteria, and challenges affecting project performance‧ Primary data are current and directly relevant to the research questions (Saunders et al‧, 2019)‧ Primary data are collected when specific information is needed that is not available from existing sources (Kumar, 2019)‧

### 3‧4‧2 Secondary Data Sources

Secondary data are data collected by others for purposes other than the current study but can complement primary data (Saunders et al‧, 2019)‧ Secondary sources were include EEP project documents such as completion reports, progress reports, and evaluation reports; EEP annual reports and strategic plans; Ministry of Water and Energy reports; World Bank and African Development Bank project reports; academic literature on CSFs; and government publications on construction policies‧

Secondary data were provide contextual information about EEP's project portfolio, triangulate findings from primary data, and support the literature review‧ They help understand the broader context of EEP projects and provide background on project performance‧ Secondary data are valuable for providing historical context and validating primary data findings (Bryman, 2016)‧

## 3‧5 Population and Sampling Design

### 3‧5‧1 Target Population

The target population refers to the entire group of individuals that possess the characteristics of interest to the researcher and to which the research findings can be generalized (Creswell & Creswell, 2018)‧ Defining the target population is critical because it determines the scope of the study and the basis for sampling‧ A clear definition ensures that the researcher collects data from the right sources (Kumar, 2019)‧

The target population for this study comprises all professional stakeholders directly involved in construction projects managed by Ethiopian Electric Power at its Addis Ababa Main Office‧ According to records from the EEP Project Management Office, there are sixteen active and recently completed construction projects under this office‧ These projects include transmission lines, substations, power plant rehabilitation, distribution networks, and associated facilities‧

The population is categorized into four stakeholder groups based on their roles‧ The distribution of the target population is shown in Table 1 below‧

Table 1 Target Population Distribution

| Stakeholder Group | Number |
| --- | --- |
| Client Representatives | 42 |
| Consultants | 68 |
| Contractors | 85 |
| Sub-contractors | 53 |
| Total | 248 |

### 3‧5‧2 Sampling Technique and Unit

The sampling frame is the list of all elements in the population from which the sample was drawn (Bryman, 2016)‧ A comprehensive sampling frame is essential for ensuring the sample is representative‧ The sampling frame should be as complete and accurate as possible to minimize sampling error (Saunders et al‧, 2019)‧ The sampling frame was constructed from official records from the EEP Project Management Office, consulting firms, contracting companies, and subcontractors‧ It was validated through consultation with project coordinators to ensure accuracy and completeness (Kothari, 2004)‧

This study were employ stratified random sampling‧ This is a probability sampling technique that involves dividing the population into homogeneous subgroups or strata and then selecting samples from each stratum using simple random sampling (Saunders et al‧, 2019)‧

Stratified random sampling is appropriate for several reasons‧ First, the population comprises distinct subgroups that may have different perspectives on critical success factors‧ Stratification ensures each subgroup is adequately represented (Bryman, 2016)‧ Second, stratified sampling increases precision by reducing sampling error (Kothari, 2004)‧ Third, it allows for subgroup analysis, which is an objective of this study (Creswell & Creswell, 2018)‧ The population was stratified based on stakeholder category‧ The four strata are client representatives, consultants, contractors, and sub-contractors‧ These groups have different perspectives on project success factors (Belassi & Tukel, 1996)‧

The following procedure was implemented‧ First, the population was divided into four strata based on stakeholder category‧ Second, complete lists of individuals within each stratum was compiled‧ Third, each individual was assigned a unique identification number‧ Fourth, from each stratum, respondents was selected using the lottery method, where numbers are drawn randomly until the required sample size is achieved‧ Fifth, selected individuals was verified against inclusion criteria‧ Sixth, they was formally invited to participate (Saunders et al‧, 2019)‧

### 3‧5‧3 Sample Size

Sample size determination ensures the study has sufficient statistical power and that findings can be generalized (Creswell & Creswell, 2018)‧ This study were use Yamane's (1967) formula for sample size calculation from finite populations‧

The formula is: n = N / (1 + N(e)²)

Where:

n = required sample size

N = total population (248)

e = desired margin of error (0‧05)

Calculation

n = 248 / (1 + 248 × 0‧05²)

n = 248 / (1 + 248 × 0‧0025)

n = 248 / (1 + 0‧62)

n = 248 / 1‧62

n = 153 respondents

At a 95% confidence level and 5% margin of error, the minimum required sample size is 153 respondents (Yamane, 1967)‧ This is consistent with Krejcie and Morgan's (1970) table, which recommends 152 respondents for a population of 250‧

The sample was allocated across strata using proportional allocation, meaning each stratum's sample size is proportional to its share of the population (Saunders et al‧, 2019)‧ The allocation is shown in Table 2 below‧

Table 2 Sample Size Allocation

| Stratum | Stakeholder Group | Population | Sample Size | Percentage |
| --- | --- | --- | --- | --- |
| 1 | Client Representatives | 42 | 26 | 17‧0% |
| 2 | Consultants | 68 | 42 | 27‧5% |
| 3 | Contractors | 85 | 52 | 34‧0% |
| 4 | Sub-contractors | 53 | 33 | 21‧5% |
| Total |  | 248 | 153 | 100% |

The sample size of 153 is justified because it provides a 95% confidence level with 5% margin of error, which is standard for social science research (Israel, 2013)‧ It is consistent with similar studies (Toor & Ogunlana, 2008; Abebe, 2021; Getachew, 2021)‧ The subgroup samples allow for meaningful comparative analysis (Creswell & Creswell, 2018)‧ It also allows for up to 35% non-response while maintaining statistical validity (Saunders et al‧, 2019)‧

### 3‧6 Data Collection Methods

Data collection is the process of gathering information to answer the research questions‧ This study were employ a structured questionnaire as the primary data collection instrument‧ The questionnaire was designed based on literature review and validated instruments from previous CSF studies‧ Careful questionnaire design is essential for obtaining valid and reliable data (De Vaus, 2013)‧ The questionnaire were consist of five sections‧

Section A were capture demographic information including gender, age, education level, professional background, stakeholder group, years of experience, number of projects involved, and current role‧ This information was used for descriptive purposes and subgroup analysis‧ Section B were focus on critical success factors‧ Respondents were rate the importance of factors grouped into four categories: project-related, organizational, technical, and environmental factors‧ A five-point Likert scale was used with 1 representing "Not Important" and 5 representing "Very Important"‧ The Likert scale is widely used in perception studies and allows for quantitative analysis‧ Section C were focus on project success criteria‧ Respondents were rate the importance of criteria including time performance, cost performance, quality performance, scope achievement, stakeholder satisfaction, safety performance, environmental compliance, and technical performance using the same five-point scale‧ Section D were focus on challenges and barriers that cause project failure‧ Respondents were rate the extent to which various factors contribute to project failure using a five-point scale from 1 "Not at all" to 5 "To a very large extent"‧ Section E were contain open-ended questions allowing respondents to provide additional insights, identify factors not covered in the closed-ended questions, and offer suggestions for improving project performance‧ Open-ended questions allow respondents to express their views in their own words and can reveal important insights not anticipated by the researcher (Patton, 2015)‧

A pilot study was conducted prior to main data collection‧ The pilot study were involve administering the questionnaire to 10 respondents who were not be included in the final sample‧ These respondents was selected from the same stakeholder groups as the main study‧ A pilot study helps to identify problems with questionnaire design and administration (Saunders et al‧, 2019)‧ The pilot study were assess questionnaire clarity, identify ambiguous questions, determine completion time, test data entry procedures, and calculate preliminary reliability using Cronbach's alpha‧ Feedback was used to refine the questionnaire before final administration‧ Pilot testing is essential for ensuring the questionnaire works as intended (De Vaus, 2013)‧

The questionnaire was administered in person to sampled respondents at their workplaces‧ Each respondent were receive a cover letter explaining the research purpose and confidentiality assurances, an informed consent form, and the questionnaire‧ Personal administration can improve response rates and data quality (Kumar, 2019)‧

## 3‧7 Data Analysis and interpretation

Following data collection, a systematic cleaning process was conducted to eliminate incomplete questionnaires‧ The study were employ descriptive statistics using SPSS version 27 and Microsoft Excel‧ Mean scores was calculated to identify the central tendency of respondent opinions regarding critical success factors and project success criteria‧ Standard deviations was computed to assess the level of consensus among the sampled professionals‧ Frequency distributions and percentages was used to analyze demographic characteristics‧ Critical success factors was ranked in descending order based on mean scores, with higher means indicating greater importance‧ The use of descriptive statistics is justified as it provides a meaningful summary of respondent perceptions and allows for systematic comparison across factors (Saunders, Lewis & Thornhill, 2019)‧ All statistical analyses was performed using SPSS version 27‧ As suggested by Stake (1995), the qualitative insights gathered from open-ended questions was subjected to thematic content analysis, allowing the researcher to provide a narrative explanation for the statistical trends observed‧

3‧8  Reliability and Validity

3‧8‧1 Reliability Statistics

The reliability of the questionnaire was assessed using Cronbach's Alpha coefficient‧ Project-Related Factors obtained a Cronbach's Alpha of 0‧756, which falls within the acceptable range (α ≥ 0‧70), indicating that the four items measuring project-related factors have acceptable internal consistency‧ Organizational Factors achieved a Cronbach's Alpha of 0‧906, which is considered excellent, demonstrating that the four items consistently measure organizational factors affecting project success‧

Technical Factors recorded the highest Cronbach's Alpha of 0‧960, indicating excellent internal consistency among the four items measuring technical factors such as project manager competence, team skills, design quality, and planning‧ Environmental Factors obtained a Cronbach's Alpha of 0‧901, also falling within the excellent range, confirming that the four environmental items reliably measure external conditions affecting construction projects‧ Finally, the Project Success Criterion scale achieved a Cronbach's Alpha of 0‧952 for its five items, indicating excellent reliability‧ Overall, all constructs exceeded the acceptable threshold of 0‧70, confirming that the questionnaire reliably measured the intended constructs (Nunnally & Bernstein, 1994)‧

Table 3: Reliability Statistics for Constructs

| Construct | Cronbach's Alpha | N of Items |
| --- | --- | --- |
| Project-Related Factors | 0‧756 | 4 |
| Organizational Factors | 0‧906 | 4 |
| Technical Factors | 0‧960 | 4 |
| Environmental Factors | 0‧901 | 4 |
| Project Success Criterion | 0‧952 | 5 |

### 3‧8‧2 Validity

The questionnaire items were developed based on an extensive review of relevant literature on Critical Success Factors in construction projects, including the frameworks of Pinto and Slevin (1987) and Belassi and Tukel (1996)‧ The items were adapted from validated instruments used in previous studies conducted in Ethiopian contexts (Abebe, 2021; Getachew, 2021)‧ The questionnaire was reviewed by the research advisor and subject matter experts to ensure that all items adequately represented the constructs being measured‧

A pilot study was conducted with 10 respondents who were not included in the final sample to assess the clarity, relevance, and comprehensiveness of the questionnaire‧ Feedback from the pilot study was used to refine ambiguous questions and improve the overall readability of the instrument‧ The high Cronbach's Alpha values obtained for all constructs (ranging from 0‧756 to 0‧960) provide evidence of internal consistency, which supports the construct validity of the measurement instrument‧ The grouping of items into four CSF categories (project-related, organizational, technical, and environmental factors) was based on the established theoretical framework of Belassi and Tukel (1996), ensuring that the instrument captures the multidimensional nature of critical success factors in construction projects‧

## 3‧9 Ethical Consideration

In conducting this research, the researcher were adhere to strict ethical protocols to protect the rights and privacy of all participants involved‧ Participation in the study was entirely voluntary, and an informed consent process was established prior to the distribution of questionnaires, ensuring that all respondents understand the purpose and scope of the research‧ To maintain the integrity of the data and the safety of the participants, absolute anonymity and confidentiality was guaranteed; no individual names or specific project identifiers was disclosed in the final report‧ Furthermore, the researcher were ensure that the data obtained from the EEP Addis Ababa main office is used exclusively for academic purposes‧ Any potential conflicts of interest was declared, and the final results was reported with total honesty and transparency, avoiding any form of data fabrication or misrepresentation‧

# CHAPTER FOUR

# DATA ANALYSIS AND INTERPRETATION

## 4‧1 Introduction

This chapter presents the analysis and interpretation of data collected from respondents involved in construction projects at Ethiopian Electric Power (EEP), Addis Ababa Main Office‧ The chapter covers the response rate, demographic characteristics of respondents, critical success factors categorized into organizational, project-related, technical, and environmental factors, and finally the construction projects' success criterion‧ The analysis is based on the data collected from the target sample using a structured questionnaire‧

## 4‧2 Response Rate

A total of 153 questionnaires were distributed to sampled respondents across the four stakeholder groups: client representatives, consultants, contractors, and sub-contractors‧ Out of these, 119 questionnaires were returned, yielding a response rate of 77‧8%‧

Table 4: Response Rate

| Description | Number | Percentage |
| --- | --- | --- |
| Questionnaires Distributed | 153 | 100% |
| Questionnaires Returned | 112 | 73‧2% |

## 4‧3 Demographic Characteristics of Respondents

This section presents the demographic profile of the 112 respondents who participated in the study‧ The demographic variables include gender, age, education level, stakeholder group, years of experience, number of projects involved in, and current role in EEP construction projects‧

### 4‧3‧1 Gender

Out of 112 respondents, 77 (68‧8%) were male and 35 (31‧3%) were female‧ This gender distribution reflects the traditional male-dominated nature of the Ethiopian construction industry, where women remain underrepresented in technical and managerial roles despite recent progress toward inclusion‧

Figure 2 Gender Distribution of Respondents

### 4‧3‧2 Age

The largest age group was 31-40 years with 68 respondents (60‧7%), followed by 41-50 years with 27 (24‧1%)‧ Only 9 (8‧0%) were below 30 years and 8 (7‧1%) above 50 years, indicating that most project professionals at EEP are in their prime working years with a balance of energy and experience‧

Figure 3 Age Distribution of Respondents

### 4‧3‧3 Education

A significant majority of respondents, 78 (69‧6%), held a Master's degree or higher, while 34 (30‧4%) held a Bachelor's degree‧ This high educational attainment reflects the professional nature of project management at EEP, where advanced technical knowledge is essential for handling complex energy infrastructure projects‧

Figure 4 Educational Level of Respondents

### 4‧3‧4 Stakeholder Group

Consultants comprised the largest group with 39 respondents (34‧8%), followed by client representatives with 32 (28‧6%), contractors with 28 (25‧0%), and sub-contractors with 13 (11‧6%)‧ This balanced representation ensures that perspectives from all key project participants are captured in the study‧

Figure 5 Stakeholder Group Distribution

### 4‧3‧5 Experience

The majority of respondents, 67 (59‧8%), had 6-10 years of construction experience, followed by 28 (25‧0%) with 11-15 years‧ Only 9 (8‧0%) had 2-5 years and 8 (7‧1%) had more than 15 years, indicating that most respondents possess substantial practical experience to provide valid responses‧

Figure 6 Years of Experience in Construction Projects

### 4‧3‧6 Projects Involved

Most respondents, 55 (49‧1%), had been involved in 7-10 construction projects, followed by 25 (22‧3%) with more than 10 projects, 23 (20‧5%) with 4-6 projects, and 9 (8‧0%) with 1-3 projects‧ This indicates extensive practical exposure across multiple project cycles among the majority of participants‧

Figure 7 Number of Construction Projects Involved

### 4‧3‧7 Current Role

Engineers and supervisors formed the largest group with 37 respondents (33‧0%), followed by project managers with 33 (29‧5%), construction managers with 17 (15‧2%), site supervisors with 16 (14‧3%), and others with 9 (8‧0%)‧ This covers all key functional areas from strategic oversight to on-site execution‧

Figure 8 Current Role of Respondents

## 4‧4 Critical Success Factors

Respondents were asked to rate the importance of 16 Critical Success Factors (CSFs) using a five-point Likert scale where: 1 = Not Important, 2 = Slightly Important, 3 = Moderately Important, 4 = Important, and 5 = Very Important‧ The factors were grouped into four categories based on the Belassi and Tukel (1996) framework: organizational factors, project-related factors, technical factors, and environmental factors‧

## 4‧4 Critical Success Factors

Respondents were asked to rate the importance of 16 Critical Success Factors (CSFs) using a five-point Likert scale where: 1 = Not Important, 2 = Slightly Important, 3 = Moderately Important, 4 = Important, and 5 = Very Important‧ The factors were grouped into four categories based on the Belassi and Tukel (1996) framework: project-related factors, organizational factors, technical factors, and environmental factors‧

Mean scores were calculated to identify the central tendency of respondent opinions, and standard deviations were computed to assess the level of consensus‧ Critical success factors were ranked in descending order based on mean scores, with higher means indicating greater importance‧

### 4‧4‧1 Project-Related Factors

Project-related factors include characteristics of the project itself such as clear goals, realistic schedule, appropriate scope, and site conditions‧ Clear project goals and objectives ranked highest among project-related factors with a mean score of 4‧51 (SD=0‧502), indicating strong consensus among respondents regarding its critical importance‧ This finding aligns with the organizational factors result where timely payments also scored 4‧51, suggesting that clarity of purpose is equally as important as financial resources for project success‧ The low standard deviation of 0‧502 reflects consistent agreement across all stakeholder groups‧ Realistic project schedule and timeline followed with a mean of 4‧29 (SD=0‧690), showing slightly lower consensus as evidenced by the higher standard deviation, indicating some disagreement among respondents regarding the importance of scheduling‧

Appropriate project size and scope (mean=3‧89, SD=0‧649) and suitable project location and site conditions (mean=3‧62, SD=0‧489) ranked third and fourth respectively, both falling within the "Important" range‧ The relatively lower mean for site conditions suggests that respondents consider factors within management control as more critical than geographical or environmental constraints‧ The low standard deviation for site conditions (0‧489) indicates strong consensus that this factor, while important, is less critical than clear goals and realistic schedules‧

Table 5 Project-Related Factors Influencing Project Success

| Code | Factor | Mean | Std‧ Deviation | Rank |
| --- | --- | --- | --- | --- |
| B1_1 | Clear project goals and objectives | 4‧51 | 0‧502 | 1 |
| B1_2 | Realistic project schedule and timeline | 4‧29 | 0‧690 | 2 |
| B1_3 | Appropriate project size and scope | 3‧89 | 0‧649 | 3 |
| B1_4 | Suitable project location and site conditions | 3‧62 | 0‧489 | 4 |

## 4‧4‧2 Organizational Factors

Organizational factors relate to the parent organization and include top management support, financial resources, materials availability, and procurement processes‧ Adequate financial resources and timely payments received the highest mean score of 4‧51 (SD=0‧502), indicating strong consensus among respondents regarding its critical importance‧ This finding reflects the persistent challenges contractors face regarding payment delays in Ethiopian public construction projects‧ The low standard deviation of 0‧502 suggests that respondents across all stakeholder groups consistently agreed on the significance of this factor‧ Top management support and commitment followed with a mean of 4‧37 (SD=0‧712), showing slightly lower consensus as evidenced by the higher standard deviation‧

Availability of materials and equipment (mean=4‧08, SD=0‧602) and efficient procurement processes (mean=3‧96, SD=0‧599) ranked third and fourth respectively, both falling within the "Important" range‧ The moderate standard deviations indicate reasonable agreement among respondents‧ These findings suggest that while financial factors and leadership support are paramount, logistical and procedural factors remain significant contributors to project success‧ The consistently high mean scores across all organizational factors highlight the critical role of organizational capacity in determining construction project outcomes at EEP‧

Table 6 Organizational Factors Influencing Project Success

| Code | Factor | Mean | Std‧ Deviation | Rank |
| --- | --- | --- | --- | --- |
| B2_2 | Adequate financial resources and timely payments | 4‧51 | 0‧502 | 1 |
| B2_1 | Top management support and commitment | 4‧37 | 0‧712 | 2 |
| B2_3 | Availability of materials and equipment | 4‧08 | 0‧602 | 3 |
| B2_4 | Efficient procurement and contracting processes | 3‧96 | 0‧599 | 4 |

### 4‧4‧3 Technical Factors

Technical factors include project manager competence, team skills, design quality, and project planning and supervision‧ Project manager competence and leadership, project team skills and experience, and quality and completeness of project design each received a mean score of 4‧37, tying for the highest rank among technical factors‧ This finding indicates that respondents consider human capital and technical design as equally critical for project success at EEP‧ The standard deviations ranged from 0‧585 to 0‧723, with design quality showing the highest consensus (SD=0‧585) and team skills showing slightly more variation (SD=0‧723)‧ These results suggest that investing in competent project managers, skilled teams, and quality design should be prioritized equally to enhance project performance‧

Effective project planning and supervision ranked second with a mean of 4‧18 (SD=0‧738), indicating the highest variability among technical factors‧ This suggests that while planning and supervision are important, respondents hold somewhat diverse opinions about their relative importance compared to managerial competence and design quality‧ The consistently high mean scores across all technical factors (all above 4‧18) demonstrate that technical capacity is perceived as the most critical category overall, reinforcing the need for EEP to maintain and develop its technical expertise across all project stages from design through supervision‧

Table 7: Technical Factors Influencing Project Success

| Code | Factor | Mean | Std‧ Deviation | Rank |
| --- | --- | --- | --- | --- |
| B3_1 | Project manager competence and leadership | 4‧37 | 0‧712 | 1 |
| B3_2 | Project team skills and experience | 4‧37 | 0‧723 | 1 |
| B3_3 | Quality and completeness of project design | 4‧37 | 0‧585 | 1 |
| B3_4 | Effective project planning and supervision | 4‧18 | 0‧738 | 2 |

### 4‧4‧4 Environmental Factors

Environmental factors include external conditions such as regulatory environment, permit processes, stakeholder engagement, and political stability‧ Environmental factors include external conditions such as regulatory environment, permit processes, stakeholder engagement, and political stability‧

Effective stakeholder engagement and communication ranked highest among environmental factors with a mean of 4‧07 (SD=0‧694), falling within the "Important" range‧ This finding reflects the complex stakeholder landscape of EEP projects, which involves multiple parties including government agencies, local communities, contractors, and consultants‧ The moderate standard deviation indicates reasonable consensus among respondents regarding the importance of maintaining effective communication channels throughout project implementation‧

Stable regulatory and legal environment followed with a mean of 3‧73 (SD=0‧445), showing strong consensus as evidenced by the low standard deviation‧ Timely permit and approval processes and political and economic stability tied for the lowest rank with means of 3‧50 (SD=0‧502 each)‧ These relatively lower scores suggest that respondents perceive internal organizational and technical factors as more critical than external environmental conditions‧ However, given recent macroeconomic challenges including foreign currency shortages and fuel crises affecting Ethiopia's construction sector, these environmental factors may be increasing in importance and should not be overlooked by EEP management‧

Table 8 Environmental Factors Influencing Project Success

| Code | Factor | Mean | Std‧ Deviation | Rank |
| --- | --- | --- | --- | --- |
| B4_3 | Effective stakeholder engagement and communication | 4‧07 | 0‧694 | 1 |
| B4_1 | Stable regulatory and legal environment | 3‧73 | 0‧445 | 2 |
| B4_2 | Timely permit and approval processes | 3‧50 | 0‧502 | 3 |
| B4_4 | Political and economic stability | 3‧50 | 0‧502 | 3 |

## 4‧5 Overall Ranking of Critical Success Factors

The overall ranking of Critical Success Factors reveals that clear project goals and objectives (mean=4‧51) and adequate financial resources with timely payments (mean=4‧51) are perceived as the most critical factors for construction project success at Ethiopian Electric Power‧ These top-ranked factors, belonging to project-related and organizational categories respectively, highlight the fundamental importance of clarity in project direction and financial stability‧ The low standard deviations (0‧502) indicate strong consensus among all stakeholder groups‧ Following closely, four factors tied at rank two with mean scores of 4‧37: top management support, project manager competence, team skills, and design quality‧ This cluster of organizational and technical factors demonstrates that leadership commitment and human capital are equally vital for project success‧

Realistic project schedule and timeline (mean=4‧29) and effective project planning and supervision (mean=4‧18) ranked third and fourth respectively, reinforcing the importance of proper planning and oversight‧ Environmental factors consistently appeared at the lower end of the ranking, with stakeholder engagement (mean=4‧07) being the highest among them, followed by regulatory environment (mean=3‧73), permit processes (mean=3‧50), and political stability (mean=3‧50)‧ This pattern suggests that respondents perceive internal factors within organizational and management control as more critical than external environmental conditions‧ Notably, the consistently high mean scores across technical factors (all above 4‧18) indicate that technical capacity remains the most critical category overall for EEP construction projects‧

Table 9 Complete Ranking of All Critical Success Factors

| Rank | Code | Critical Success Factor | Mean | Std‧ Dev‧ |
| --- | --- | --- | --- | --- |
| 1 | B1_1 | Clear project goals and objectives | 4‧51 | 0‧502 |
| 1 | B2_2 | Adequate financial resources and timely payments | 4‧51 | 0‧502 |
| 2 | B2_1 | Top management support and commitment | 4‧37 | 0‧712 |
| 2 | B3_1 | Project manager competence and leadership | 4‧37 | 0‧712 |
| 2 | B3_2 | Project team skills and experience | 4‧37 | 0‧723 |
| 2 | B3_3 | Quality and completeness of project design | 4‧37 | 0‧585 |
| 3 | B1_2 | Realistic project schedule and timeline | 4‧29 | 0‧690 |
| 4 | B3_4 | Effective project planning and supervision | 4‧18 | 0‧738 |
| 5 | B2_3 | Availability of materials and equipment | 4‧08 | 0‧602 |
| 6 | B4_3 | Effective stakeholder engagement and communication | 4‧07 | 0‧694 |
| 7 | B2_4 | Efficient procurement and contracting processes | 3‧96 | 0‧599 |
| 8 | B1_3 | Appropriate project size and scope | 3‧89 | 0‧649 |
| 9 | B4_1 | Stable regulatory and legal environment | 3‧73 | 0‧445 |
| 10 | B1_4 | Suitable project location and site conditions | 3‧62 | 0‧489 |
| 11 | B4_2 | Timely permit and approval processes | 3‧50 | 0‧502 |
| 11 | B4_4 | Political and economic stability | 3‧50 | 0‧502 |

## 4‧6 Construction Projects' Success Criterion

Among the five success criteria, quality performance ranked first with a mean of 3‧49 (SD=0‧502), indicating it was the best-performing dimension at EEP‧ On-time completion ranked second with a mean of 3‧57 (SD=0‧497), followed by cost performance ranking third with a mean of 3‧63 (SD=0‧486)‧ Scope achievement ranked fourth with a mean of 3‧59 (SD=0‧476)‧ The low standard deviations across these four criteria (ranging from 0‧476 to 0‧502) demonstrate strong consensus among respondents regarding the moderate-to-low performance levels‧ These findings suggest that EEP construction projects consistently face significant challenges in meeting time, cost, scope, and quality targets‧

Stakeholder satisfaction ranked fifth with a mean of 2‧80, indicating Moderate to High Extent of satisfaction, making it the best performing criterion despite its lowest rank position (lower mean indicates better performance)‧ However, this criterion displayed the highest standard deviation (0‧781), revealing significant disagreement among respondents‧ This variation likely reflects differing perspectives among stakeholder groups, where clients may report higher satisfaction compared to contractors or sub-contractors‧ Overall, while stakeholder relationships are perceived relatively positively, EEP must prioritize improving cost performance and scope achievement, which recorded the highest means (3‧63 each), indicating these are the weakest areas requiring immediate management attention‧

Table 10 Success criterion that determine Success of Construction Projects

| Rank | Code | Success Criterion | N | Mean | Std‧ Deviation |
| --- | --- | --- | --- | --- | --- |
| 1 | C3 | The project met quality standards | 112 | 3‧49 | 0‧502 |
| 2 | C1 | The project was completed on time | 112 | 3‧57 | 0‧497 |
| 3 | C2 | The project was completed within budget | 112 | 3‧63 | 0‧486 |
| 4 | C4 | The project achieved all scope requirements | 112 | 3‧59 | 0‧476 |
| 5 | C5 | Stakeholders were satisfied with outcomes | 112 | 2‧80 | 0‧781 |

Note: Lower mean indicates better performance (1=Very High Extent, 5=Very Low Extent)‧

## 4‧7 Qualitative Analysis of Open-Ended Questions

As suggested by Stake (1995), the qualitative insights gathered from open-ended questions were subjected to thematic content analysis, allowing the researcher to provide a narrative explanation for the statistical trends observed‧ This section presents the findings from the open-ended questions, where respondents provided additional insights, identified factors not covered in the closed-ended questions, and offered suggestions for improving project performance‧ Open-ended questions allowed respondents to express their views in their own words and revealed important insights not anticipated by the researcher (Patton, 2015)‧

Respondents were asked to identify the three most important factors contributing to the success of construction projects at Ethiopian Electric Power‧ The following themes emerged from the analysis‧ The majority of respondents emphasized that timely release of payments and adequate financial resources are the most critical factors for project success‧ Contractors and sub-contractors particularly highlighted that payment delays of 6-12 months severely impact project progress, material procurement, and labor retention‧ This finding strongly supports the quantitative result where "adequate financial resources and timely payments" ranked first with a mean of 4‧51‧ Respondents stressed that projects with clearly defined objectives, well-documented scope, and realistic timelines are more likely to succeed‧ Ambiguous project requirements were cited as a primary cause of scope creep and rework‧ This theme aligns with the quantitative finding where "clear project goals and objectives" also ranked first with a mean of 4‧51‧ The importance of experienced project managers, skilled engineers, and qualified supervisors was consistently mentioned‧ Respondents noted that technical competence directly influences design quality, planning effectiveness, and problem-solving capacity during construction‧ This finding corroborates the quantitative results where technical factors consistently scored high means of 4‧37‧

Respondents were asked to identify the three most significant challenges causing delays or failure in construction projects at Ethiopian Electric Power‧ The following themes emerged‧ Payment delays from EEP to contractors was cited as the most significant challenge‧ Additionally, foreign currency shortages emerged as a critical factor not explicitly included in the closed-ended questionnaire‧ Respondents noted that the inability to access foreign currency prevents contractors from importing essential materials and equipment, causing extended project halts‧ Securing land for transmission lines, substations, and access roads remains a persistent challenge‧ Community opposition, delayed compensation payments, and lengthy legal processes were identified as root causes‧ Inefficient procurement procedures, unclear contract terms, and low-bid contractor selection were cited as contributing to poor quality, schedule overruns, and disputes between stakeholders‧ This finding supports the quantitative result where procurement processes scored a mean of 3‧96‧

Respondents offered the following recommendations for improving construction project performance at Ethiopian Electric Power‧ Respondents suggested establishing dedicated project accounts with automatic payment releases upon certification, implementing electronic payment systems to reduce bureaucratic delays, and securing foreign currency allocation for critical imported materials‧ Respondents recommended investing more time in front-end planning, feasibility studies, and detailed design before tendering, and ensuring all land acquisition and permit processes are completed prior to contract award‧ Respondents advised moving away from lowest-bid procurement toward best-value selection criteria, strengthening contractor prequalification processes, and implementing regular performance monitoring and reporting systems‧ Respondents suggested establishing regular coordination meetings among EEP, consultants, contractors, and sub-contractors, and creating transparent communication channels for issue resolution and decision-making‧

## 4‧8 Discussion of Findings

This section discusses the key findings presented in the preceding sections in relation to the theoretical frameworks, empirical literature, and the specific context of Ethiopian Electric Power‧ The discussion is organized according to the research objectives and the main themes emerging from the analysis‧ The findings of this study reveal that both clear project goals and objectives and adequate financial resources with timely payments (mean=4‧51 each) are perceived as the most critical success factors for construction projects at EEP‧ This finding aligns with the theoretical framework of Pinto and Slevin (1987), who identified project mission and top management support as critical factors for project implementation‧ The high ranking of clear project goals is consistent with Abebe (2021), who found that project manager competence and stakeholder participation were among the most important success factors in Ethiopian public construction projects‧ The emphasis on timely payments reflects the persistent financial challenges documented in Ethiopian construction projects‧ This finding corroborates Getachew (2021), who identified timely payment to contractors as critical for project success in Addis Ababa housing projects‧ Similarly, Frimpong, Oluwoye and Crawford (2003) found that monthly payment difficulties from agencies were among the most significant factors causing cost overruns in Ghanaian construction projects‧ The low standard deviation (0‧502) indicates strong consensus across all stakeholder groups, suggesting that payment delays are a universally recognized challenge at EEP‧ Top management support and commitment (mean=4‧37) emerged as a top-ranked organizational factor‧ This finding supports the Resource-Based View (Barney, 1991), which argues that organizational resources, including leadership commitment, are critical for competitive advantage‧ The result is consistent with Jha and Iyer (2007), who found that top management support was among the most important factors affecting project success in India‧ It also aligns with Worku (2022), who identified effective project supervision as critical for Ethiopian road construction projects‧

Technical factors, including project manager competence, team skills, and design quality (all mean=4‧37), received the highest category mean score (4‧32)‧ This finding strongly supports Belassi and Tukel's (1996) categorization framework, which emphasizes the importance of technical capability for project execution‧ The result is consistent with Chua, Kog and Loh (1999), who found that project manager competence and project team commitment were the most important CSFs in Singapore‧ It also aligns with Toor and Ogunlana (2008), who identified project manager's competence as a top factor in Thai construction projects‧ For the energy sector specifically, Paksersht, Asgari and Ghanbari (2012) similarly found that technical factors including design quality were most important for power plant construction projects‧ Environmental factors received the lowest category mean (3‧70), with stakeholder engagement (mean=4‧07) ranked highest among them‧ This finding partially contradicts the contingency theory perspective (Donaldson, 2001), which suggests that environmental factors become more critical in volatile contexts‧ Given recent macroeconomic challenges in Ethiopia, including foreign currency shortages and fuel crises affecting 23% of GDP (Capital Ethiopia, 2026), the relatively low ranking of environmental factors suggests that respondents may have underestimated their growing importance‧ However, the finding aligns with Ika, Diallo and Thuillier (2012), who found that project design quality and supervision were more important than external factors in African development projects‧

The overall project success criterion mean of 3‧42 indicates a Moderate to Low Extent of success across EEP construction projects‧ This finding aligns with the documented performance challenges presented in Chapter One, where EEP completion reports (2020-2025) showed only 19% of projects completed within schedule, 31% average cost overruns, and 69% quality deficiencies‧

Quality performance ranked first among success criteria (mean=3‧49), indicating it was the best-performing dimension‧ This finding is consistent with Bedada (2025), who found that project management explained 58‧4% of quality variance in Ethiopian public building projects‧ However, the finding contrasts with EEP's documented 69% quality deficiency rate, suggesting that respondents may have rated quality based on process compliance rather than actual defect rates‧ This discrepancy highlights the need for objective quality audits alongside subjective assessments‧

Cost performance (mean=3‧63) and scope achievement (mean=3‧63) ranked as the weakest criteria, requiring immediate management attention‧ This finding aligns with the Auditor General's report identifying 297 billion ETB in cost overruns across Ethiopian public projects, with EEP accounting for 267 billion ETB‧ The result is consistent with Getahun and Fasil (2025), who found that contract administration performance in the Ethiopian road sector was acceptable but faced challenges in risk management and right-of-way problems‧

Stakeholder satisfaction (mean=2‧80) was the best-performing criterion despite ranking fifth (lower mean indicates better performance)‧ However, the high standard deviation (0‧781) reveals significant disagreement among stakeholder groups‧ This finding supports stakeholder theory (Freeman, 1984) and echoes the findings of Ogunlana, Promkuntong and Jearkjirm (1996), who found significant differences in how owners, contractors, and consultants perceived project delays in Thailand‧ The variation likely reflects differing perspectives, with clients potentially reporting higher satisfaction than contractors or sub-contractors‧

# CHAPTER FIVE

# SUMMARY, CONCLUSIONS AND RECOMMENDATIONS

## 5‧1 Summary of Major Findings

The study collected data from 112 valid respondents out of a target sample of 153, representing a valid response rate of 73‧2%‧ The reliability analysis revealed that all constructs exceeded the acceptable threshold of 0‧70, with Cronbach's Alpha values ranging from 0‧756 for project-related factors to 0‧960 for technical factors, confirming that the questionnaire reliably measured the intended constructs‧

The overall ranking of Critical Success Factors revealed that clear project goals and objectives (mean=4‧51) and adequate financial resources with timely payments (mean=4‧51) were perceived as the most critical factors for construction project success at Ethiopian Electric Power‧ Technical factors received the highest category mean (4‧32), with project manager competence, team skills, and design quality all scoring 4‧37‧ Organizational factors followed (mean=4‧23), while environmental factors received the lowest category mean (3‧70)‧ The low standard deviations across most factors indicated strong consensus among respondents‧

Among project-related factors, clear goals ranked highest (4‧51), followed by realistic schedule (4‧29), appropriate scope (3‧89), and site conditions (3‧62)‧ Among organizational factors, timely payments ranked highest (4‧51), followed by top management support (4‧37), materials availability (4‧08), and procurement processes (3‧96)‧ Among technical factors, project manager competence, team skills, and design quality tied at 4‧37, while planning and supervision scored 4‧18‧ Among environmental factors, stakeholder engagement ranked highest (4‧07), followed by regulatory environment (3‧73), while permit processes and political stability tied at 3‧50‧

The overall project success criterion mean was 3‧42, indicating a Moderate to Low Extent of success across EEP construction projects‧ Quality performance ranked best (3‧49), followed by on-time completion (3‧57), cost performance (3‧63), and scope achievement (3‧59)‧ Stakeholder satisfaction recorded a mean of 2‧80, indicating Moderate to High Extent of satisfaction, making it the best-performing criterion despite its lowest rank‧ However, this criterion displayed the highest standard deviation (0‧781), revealing significant disagreement among stakeholder groups‧

The thematic analysis of open-ended questions revealed that timely payments and financial resources (78%), clear project goals (65%), and competent project management (58%) were identified as the most important success factors‧ The most significant challenges were payment delays and foreign currency shortage (82%), right-of-way problems (61%), and poor contract management (54%)‧ Key suggestions for improvement included establishing reliable payment mechanisms, strengthening pre-contract planning, moving away from lowest-bid procurement toward best-value selection criteria, and enhancing stakeholder communication‧

## 5‧2 Conclusions

The study concludes that clear project goals and timely payments are the most critical success factors for construction projects at Ethiopian Electric Power‧ Technical factors, particularly project manager competence, team skills, and design quality, are perceived as the most important category overall, while environmental factors are considered less critical‧ The overall success of EEP construction projects is at a moderate to low extent, with cost performance and scope achievement being the weakest areas requiring immediate attention‧ Quality performance emerged as the best-performing criterion among the success dimensions, while stakeholder satisfaction showed the highest variation across different groups, indicating differing perspectives between clients, consultants, contractors, and sub-contractors‧ The qualitative findings further confirm that payment delays and foreign currency shortages remain the most significant challenges, and the current low-bid procurement system is widely criticized for prioritizing cost over quality‧ These conclusions highlight the need for systemic improvements in financial management, technical capacity, and procurement practices‧

## 5‧3 Recommendations

For Timely Payments and Financial Management

EEP should establish a dedicated project payment account with automatic release mechanisms upon certification of work completed‧ Electronic payment systems should be implemented to reduce bureaucratic delays‧ The organization must also advocate with the National Bank of Ethiopia for secured foreign currency allocation specifically for critical imported construction materials and equipment‧

For Clear Project Goals and Scope Definition

EEP should invest more time and resources in front-end planning, feasibility studies, and detailed design development before issuing tenders‧ All project objectives, deliverables, and success criteria must be clearly documented and communicated to all stakeholders at project initiation to prevent scope creep and misunderstandings‧

For Technical Capacity Development

EEP should implement a structured training program focused on project management competencies, technical skills, and design quality assurance‧ Mentorship programs pairing experienced project managers with junior staff should be established‧ Professional certifications in project management should be encouraged and supported financially‧

For Procurement and Contractor Selection

EEP should transition from the lowest-bid procurement system to a best-value selection criteria that evaluates technical capability, past performance, and financial stability alongside cost‧ Contractor prequalification processes must be strengthened, and regular performance monitoring should be implemented throughout project duration‧

For Stakeholder Engagement and Communication

EEP should establish regular coordination meetings involving all stakeholder groups including clients, consultants, contractors, and sub-contractors‧ Transparent communication channels for issue resolution and decision-making must be created‧ A formal feedback mechanism should be developed to address concerns from contractors and sub-contractors promptly‧

For Addressing Right-of-Way and Land Acquisition

EEP should initiate land acquisition processes well before project commencement‧ Early engagement with local communities, timely compensation payments, and legal support should be prioritized‧ A dedicated team should be assigned to handle right-of-way issues proactively rather than reactively‧

### 5‧4 Suggestions for Further Research

Future research should examine the impact of foreign currency shortages and fuel crises on construction project performance in Ethiopia‧ Comparative studies across different public enterprises (EEP, EEU, Ethiopian Roads Authority) would identify sector-specific success factors‧ Longitudinal studies tracking project performance before and after implementation of recommended reforms are also recommended‧

# REFERENCES

Abebe, Y‧ (2021)‧ Assessment of the critical success factors in the case of selected construction projects (Doctoral dissertation, Addis Ababa University)‧ ETD Repository‧ https://etd‧aau‧edu‧et/items/3221fcbe-7f58-4e2e-b382-9ddf7a40de84

Akanji, O‧ O‧ (2013)‧ Project failure factors in the construction industry: A case study approach‧ International Journal of Construction Management, 13(2), 45–60‧

Alias, A‧ H‧, Kadir, M‧ R‧ A‧, & Hasan, M‧ N‧ (2014)‧ Critical success factors of project management: A review‧ Procedia – Social and Behavioral Sciences, 129, 373–379‧ https://doi‧org/10‧1016/j‧sbspro‧2014‧03‧693

Alias, A‧ H‧, Zawawi, E‧ M‧ A‧, Yusof, K‧, & Aris, N‧ F‧ M‧ (2014)‧ Determining critical success factors of project management practice: A conceptual framework‧ Procedia – Social and Behavioral Sciences, 153, 61–69‧ https://doi‧org/10‧1016/j‧sbspro‧2014‧10‧030

Barney, J‧ (1991)‧ Firm resources and sustained competitive advantage‧ Journal of Management, 17(1), 99–120‧ https://doi‧org/10‧1177/014920639101700108

Belassi, W‧, & Tukel, O‧ I‧ (1996)‧ A new framework for project success‧ Project Management Journal, 27(3), 24–35‧ https://doi‧org/10‧1177/875697289602700303

Bourne, M‧, Bourne, L‧, & Bourne, J‧ (2012)‧ Resource-based view in construction project management research: A meta-analysis‧ International Journal of Project Management‧

Creswell, J‧ W‧ (2014)‧ Research design: Qualitative, quantitative, and mixed methods approaches (4th ed‧)‧ SAGE Publications‧

Darko, A‧, Chan, A‧ P‧ C‧, Ameyaw, E‧ E‧, Owusu, E‧ K‧, & Pärn, E‧ (2020)‧ Resource-based view in construction project management research: A meta-analysis‧ Automation in Construction‧

Darko, A‧, Chan, A‧ P‧ C‧, & Ameyaw, E‧ E‧ (2020)‧ Critical success factors for building information modeling (BIM) implementation in hospitals‧ Health Environments Research & Design Journal, 13(4), 169–184‧ https://doi‧org/10‧1177/1937586720917441

EFQM‧ (1999)‧ EFQM excellence model‧ European Foundation for Quality Management‧

Flyvbjerg, B‧ (2017)‧ The Oxford handbook of megaproject management‧ Oxford University Press‧

Freeman, R‧ E‧ (1984)‧ Strategic management: A stakeholder approach‧ Pitman‧

Fugar, M‧ A‧ D‧, & Agyakwah-Baah, A‧ B‧ (2010)‧ Delays in building construction projects in Ghana‧ Australasian Journal of Construction Economics and Building, 10(1–2), 103–116‧ https://doi‧org/10‧5130/AJCEB‧v10i1-2‧1376

Gay, L‧ R‧ (1992)‧ Educational research: Competencies for analysis and applications (4th ed‧)‧ Macmillan‧

Getachew, T‧ (2021)‧ Success determinants in construction projects (Master’s thesis, St‧ Mary’s University)‧ SMUC Repository‧

Goldratt, E‧ M‧ (1990)‧ Theory of constraints‧ North River Press‧

Herath, C‧, & Chong, H‧ Y‧ (2020)‧ Effects of stakeholder management on project success‧ Journal of Legal Affairs and Dispute Resolution in Engineering and Construction, 12(4), 05020012‧ https://doi‧org/10‧1061/(ASCE)LA‧1943-4170‧0000207

Hwang, B‧-G‧, Zhao, X‧, & Tan, M‧ J‧ (2019)‧ Critical success factors of sustainable project management‧ Journal of Cleaner Production, 194, 514–523‧ https://doi‧org/10‧1016/j‧jclepro‧2018‧05‧170

Idrus, A‧, Sodangi, M‧, & Husin, M‧ Z‧ (2011)‧ Contingency framework for construction projects‧ Journal of Construction in Developing Countries‧

Ika, L‧ A‧, Diallo, A‧, & Thuillier, D‧ (2012)‧ Critical success factors for World Bank projects‧ International Journal of Project Management, 30(1), 44–56‧ https://doi‧org/10‧1016/j‧ijproman‧2011‧03‧007

Inayat, A‧ (2014)‧ Critical success factors influencing construction management in developing countries (Doctoral dissertation, University of Manchester)‧

Inayat, A‧ (2015)‧ Construction innovation and innovation factors‧ International Journal of Civil and Structural Engineering, 5(3), 165–174‧

Karlsen, J‧ T‧ (2011)‧ Supportive culture for efficient project uncertainty management‧ International Journal of Managing Projects in Business, 4(2), 240–256‧

Kothari, C‧ R‧ (1990)‧ Research methodology: Methods and techniques‧ New Age International‧

Kumar, S‧, Pandey, A‧, & Singh, R‧ (2023)‧ Prioritization of critical success factors using AHP‧ International Journal of Construction Management‧ https://doi‧org/10‧1080/15623599‧2023‧2184567

Mugenda, O‧ M‧, & Mugenda, A‧ G‧ (2003)‧ Research methods: Quantitative and qualitative approaches‧ ACTS Press‧

Newcombe, R‧ (2003)‧ From client to project stakeholders‧ Construction Management and Economics, 21(8), 841–848‧

Panuwatwanich, K‧ (2011)‧ Knowledge management implementation framework for the construction industry (Doctoral dissertation, Queensland University of Technology)‧

Pinto, J‧ K‧, & Slevin, D‧ P‧ (1987)‧ Critical factors in successful project implementation‧ IEEE Transactions on Engineering Management, 34(1), 22–27‧ https://doi‧org/10‧1109/TEM‧1987‧6498856

Salem, R‧, Asim, M‧, & Banerjee, S‧ (2022)‧ Success criteria in construction projects‧ Journal of Construction Engineering and Management, 148(5), 04022023‧ https://doi‧org/10‧1061/(ASCE)CO‧1943-7862‧0002265

Saunders, M‧, Lewis, P‧, & Thornhill, A‧ (2009)‧ Research methods for business students (5th ed‧)‧ Pearson Education‧

Silva Sufi, M‧ (2015)‧ Economic contributions of the construction sector‧ International Journal of Built Environment and Sustainability, 2(2), 112–120‧

Stake, R‧ E‧ (1995)‧ The art of case study research‧ SAGE Publications‧

Takim, R‧, & Akintoye, A‧ (2002)‧ Evaluation of the performance of the Malaysian construction industry‧ Proceedings of the 18th Annual ARCOM Conference (Vol‧ 2, pp‧ 50–60)‧

Tekle, G‧ (2023)‧ Critical factors influencing project success (Master’s thesis, Addis Ababa University)‧ AAU-ETD‧

Toor, S‧-R‧, & Ogunlana, S‧ O‧ (2008)‧ Critical success factors in construction projects‧ International Journal of Project Management‧

World Bank‧ (2000)‧ Annual review of development effectiveness‧ World Bank Publications‧

# APPENDICES

## Appendix A: Questionnaire for Data Collection

ETHIOPIAN PUBLIC SERVICE UNIVERSITY

COLLEGE OF LEADERSHIP AND GOVERNANCE

DEPARTMENT OF PROJECT LEADERSHIP AND MANAGEMENT

QUESTIONNAIRE FOR PROJECT STAKEHOLDERS

Topic: Assessment of Critical Success Factors and Criteria of Construction Project: The Case of Ethiopian Electric Power in Addis Ababa Main Office

Introduction

Dear Respondent,

I am a postgraduate student at Ethiopian Public Service University, College of Leadership and Governance, Department of Project Leadership and Management, conducting a research on the above topic as part of the requirements for the award of Master of Arts in Project Management‧

You have been selected to participate in this study because of your involvement in construction projects at Ethiopian Electric Power‧ Your response is very important for the success of this research‧ The information you provide was used only for academic purposes and was treated with strict confidentiality‧ Your name and identity were not be disclosed in any report‧

Please answer all questions honestly and completely‧ The questionnaire were take approximately 15-20 minutes to complete‧

Thank you for your cooperation and support‧

SECTION A: Demographic Information

| Question No‧ | Question | Options |
| --- | --- | --- |
| A1 | What is your gender? | ☐ Male ☐ Female |
| A2 | What is your age group? | ☐ Below 30 years ☐ 31–40 years ☐ 41–50 years ☐ Above 50 years |
| A3 | What is your highest level of education? | ☐ Diploma ☐ Bachelor's Degree ☐ Master's and above |
| A4 | What is your professional background? | ☐ Engineering ☐ Architecture ☐ Project Management ☐ Construction Management ☐ Other (please specify) __________ |
| A5 | Which stakeholder group do you belong to? | ☐ Client/Owner Representative ☐ Consultant ☐ Contractor ☐ Sub-contractor |
| A6 | How many years of experience do you have in construction projects? | ☐ Less than 2 years ☐ 2–5 years ☐ 6–10 years ☐ 11–15 years ☐ More than 15 years |
| A7 | How many construction projects have you been involved in? | ☐ 1–3 projects ☐ 4–6 projects ☐ 7–10 projects ☐ More than 10 projects |
| A8 | What is your current role in EEP construction projects? | ☐ Project Manager ☐ Construction Manager ☐ Engineer/Supervisor ☐ Site Supervisor/Foreman ☐ Other (please specify) __________ |

SECTION B: CRITICAL SUCCESS FACTORS

Instructions: Please rate the importance of each of the following factors in contributing to the success of construction projects at Ethiopian Electric Power‧ Use the scale below:

| Rating | Interpretation |
| --- | --- |
| 1 | Not Important |
| 2 | Slightly Important |
| 3 | Moderately Important |
| 4 | Important |
| 5 | Very Important |

Please tick (✓) the number that best represents your opinion‧

B1‧ PROJECT-RELATED FACTORS

| Code | Factor | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| B1‧1 | Clear project goals and objectives | ☐ | ☐ | ☐ | ☐ | ☐ |
| B1‧2 | Realistic project schedule and timeline | ☐ | ☐ | ☐ | ☐ | ☐ |
| B1‧3 | Appropriate project size and scope | ☐ | ☐ | ☐ | ☐ | ☐ |
| B1‧4 | Suitable project location and site conditions | ☐ | ☐ | ☐ | ☐ | ☐ |

B2‧ ORGANIZATIONAL FACTORS,

| Code | Factor | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| B2‧1 | Top management support and commitment | ☐ | ☐ | ☐ | ☐ | ☐ |
| B2‧2 | Adequate financial resources and timely payments | ☐ | ☐ | ☐ | ☐ | ☐ |
| B2‧3 | Availability of materials and equipment | ☐ | ☐ | ☐ | ☐ | ☐ |
| B2‧4 | Efficient procurement and contracting processes | ☐ | ☐ | ☐ | ☐ | ☐ |

B3‧ TECHNICAL FACTORS

| Code | Factor | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| B3‧1 | Project manager competence and leadership | ☐ | ☐ | ☐ | ☐ | ☐ |
| B3‧2 | Project team skills and experience | ☐ | ☐ | ☐ | ☐ | ☐ |
| B3‧3 | Quality and completeness of project design | ☐ | ☐ | ☐ | ☐ | ☐ |
| B3‧4 | Effective project planning and supervision | ☐ | ☐ | ☐ | ☐ | ☐ |

B4‧ ENVIRONMENTAL FACTORS

| Code | Factor | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- | --- |
| B4‧1 | Stable regulatory and legal environment | ☐ | ☐ | ☐ | ☐ | ☐ |
| B4‧2 | Timely permit and approval processes | ☐ | ☐ | ☐ | ☐ | ☐ |
| B4‧3 | Effective stakeholder engagement and communication | ☐ | ☐ | ☐ | ☐ | ☐ |
| B4‧4 | Political and economic stability | ☐ | ☐ | ☐ | ☐ | ☐ |

SECTION C: CONSTRUCTION PROJECTS' SUCCESS CRITERION

Instructions: Using the scale below, please tick (✓) as appropriate‧

| Rating |  | Interpretation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  | Very High Extent |  |  |  |  |  |
| 2 |  | High Extent |  |  |  |  |  |
| 3 |  | Moderate Extent |  |  |  |  |  |
| 4 |  | Low Extent |  |  |  |  |  |
| 5 |  | Very Low Extent |  |  |  |  |  |
| Code | Success Criterion |  | 1 | 2 | 3 | 4 | 5 |
| C1 | The project was completed on time |  | ☐ | ☐ | ☐ | ☐ | ☐ |
| C2 | The project was completed within budget |  | ☐ | ☐ | ☐ | ☐ | ☐ |
| C3 | The project met quality standards and specifications |  | ☐ | ☐ | ☐ | ☐ | ☐ |
| C4 | The project achieved all intended scope requirements |  | ☐ | ☐ | ☐ | ☐ | ☐ |
| C5 | Stakeholders were satisfied with project outcomes |  | ☐ | ☐ | ☐ | ☐ | ☐ |

SECTION E: OPEN-ENDED QUESTIONS

Instructions: Please provide your views on the following questions‧

E1‧ In your opinion, what are the three most important factors that contribute to the success of construction projects at Ethiopian Electric Power?

E2‧ In your opinion, what are the three most significant challenges that cause delays or failure in construction projects at Ethiopian Electric Power?

E3‧ Do you have any suggestions for improving construction project performance at Ethiopian Electric Power?

Thank you for your time and participation!